| Policy Owner: | Chief Information Security Officer / IT Manager |
| --- | --- |
| Effective Date: | January 1, 2025 |
| Version: | 1.0 |
| Classification: | Internal Use Only |

# Access Control Policy Implementation Workbook

Implementation Workbook

# Access Control Policy Implementation Workbook

## How to Use This Workbook

This workbook guides you through implementing an access control program from scratch or improving your existing one. Whether you're a 10-person startup or a 500-person enterprise, this workbook will help you build effective access controls.

What's included:- Step-by-step implementation phases
- Realistic timelines and resource estimates
- Templates and checklists you can customize
- Troubleshooting guidance for common challenges
- Quick wins you can implement immediately
- Budget guidance for tools and resources

Your implementation path:1.Phase 1 (Weeks 1-2):Foundation and assessment
2.Phase 2 (Weeks 3-6):Core access controls
3.Phase 3 (Weeks 7-10):Authentication and monitoring
4.Phase 4 (Weeks 11-14):Advanced controls and optimization
5.Phase 5 (Ongoing):Maintenance and continuous improvement

Time commitment:-Small organizations (< 50 employees):40-60 hours over 8-12 weeks
-Medium organizations (50-200 employees):80-120 hours over 12-16 weeks
-Large organizations (200+ employees):150-250 hours over 16-20 weeks

Who should be involved:- IT Manager or CISO (project lead)
- System administrators
- HR representative
- Key business stakeholders
- Executive sponsor

Before you start:- Get executive buy-in and budget approval
- Identify your implementation team
- Set aside dedicated time each week
- Communicate the project to your organization

Let's begin!

## Phase 1: Foundation and Assessment (Weeks 1-2)

### Week 1: Current State Assessment

Goal:Understand what you have today and what gaps exist.

Step 1.1: Inventory Your Systems (4-6 hours)

Create a comprehensive inventory of all systems that require access control.

What to document:- System name and purpose
- Who owns/manages it
- How many users have access
- Types of data stored (public, internal, confidential, sensitive)
- Current authentication method (username/password, SSO, MFA, etc.)
- Who approves access today
- Whether access is logged/monitored

Use this template:

| System Name | Owner | Users | Data Sensitivity | Auth Method | MFA? | Access Approval Process | Logging? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Email (Microsoft 365) | IT Manager | All (75) | Internal/Confidential | SSO | Yes | Auto on hire | Yes |
| CRM (Salesforce) | Sales VP | Sales (15) | Confidential | Username/PW | No | Manual request | No |
| Accounting (QuickBooks) | CFO | Finance (5) | Sensitive | Username/PW | No | CFO approval | No |

Tips:- Don't forget: email, file shares, cloud apps, on-premise systems, databases, admin tools
- Ask department heads to identify their critical systems
- Check your software subscriptions/licenses for a complete list
- Include physical access systems (badge readers, door locks)

Step 1.2: Document Current Access Processes (3-4 hours)

Map out how access requests work today (even if informal).

Questions to answer:- How do new hires get their initial access?
- Who approves access requests for different systems?
- How long does it typically take to grant access?
- How do you know when someone leaves?
- How is access removed when someone leaves?
- Are there written procedures for any of this?

Common discovery:Most organizations find their processes are informal, undocumented, and inconsistent across systems. That's OK—you're fixing that now!

Step 1.3: Identify Current Gaps (2-3 hours)

Compare your current state to best practices. Common gaps include:

Process gaps:- [ ] No formal access request process
- [ ] No access approval documentation
- [ ] Termination access removal is manual and inconsistent
- [ ] No regular review of who has access
- [ ] No one specifically responsible for access management

Technical gaps:- [ ] No centralized user directory (Active Directory/Azure AD/Okta)
- [ ] No MFA on critical systems
- [ ] Weak password requirements
- [ ] No SSO (users have many passwords)
- [ ] No access logging or monitoring
- [ ] No privileged access management

Documentation gaps:- [ ] No written access control policy
- [ ] No roles/responsibilities defined
- [ ] No access approval matrix
- [ ] No termination checklist
- [ ] No evidence for auditors

Step 1.4: Assess Risk and Prioritize (2-3 hours)

Not all gaps are equal. Prioritize based on risk and compliance needs.

High Priority (Fix in Phase 2-3):- Systems with sensitive data lacking MFA
- No formal termination process (ex-employees might still have access!)
- Privileged/admin accounts not properly controlled
- Systems required for compliance (SOC 2, HIPAA, PCI, etc.)

Medium Priority (Fix in Phase 3-4):- Inconsistent password policies across systems
- No access logging on important systems
- Manual, time-consuming access provisioning
- No regular access reviews

Low Priority (Nice to have, address later):- SSO for convenience (if not already implemented)
- Advanced automation
- Sophisticated PAM platform
- Biometric authentication

Deliverable:Current State Assessment Report (3-5 pages documenting findings and prioritized gaps)

### Week 2: Planning and Quick Wins

Goal:Create your implementation roadmap and implement some quick wins to build momentum.

Step 2.1: Define Your Target State (3-4 hours)

What does "done" look like for your organization?

Minimum viable access control program:- [ ] Formal access request and approval process
- [ ] MFA on email and remote access
- [ ] Strong password policy enforced
- [ ] Documented termination procedures
- [ ] Quarterly review of privileged access
- [ ] Annual review of all access
- [ ] Basic logging on critical systems

Mature access control program (add these over time):- [ ] Centralized identity management (AD/Azure AD/Okta)
- [ ] SSO for major applications
- [ ] MFA on all systems with sensitive data
- [ ] Privileged access management (PAM)
- [ ] Automated access provisioning/deprovisioning
- [ ] Real-time monitoring and alerting
- [ ] Role-based access control (RBAC)

Step 2.2: Budget and Resource Planning (2-3 hours)

Estimate costs for tools, services, and time.

Typical costs for small-medium organizations (50-200 users):

Tools:- Identity provider (Azure AD, Okta, JumpCloud): $3-8 per user/month = $150-1,600/month
- MFA solution (if not included): $3-6 per user/month = $150-1,200/month
- Password manager (enterprise): $4-8 per user/month = $200-1,600/month
- PAM platform (optional, for mature programs): $10,000-50,000/year
- SIEM/logging (if not already have): $5,000-25,000/year

Services (optional):- Security consultant to guide implementation: $5,000-15,000
- Implementation services from vendors: $2,000-10,000

Internal time:- IT staff time: 80-150 hours over 3-4 months
- Management time: 20-30 hours for approvals/decisions

Step 2.3: Get Executive Approval (1-2 hours)

Prepare a brief business case for executive approval.

Your one-page business case should include:- Current risks (ex-employees with access, weak authentication, no audit trail)
- Compliance requirements (SOC 2, customer contracts, etc.)
- Cost of data breach vs. cost of controls
- Proposed budget and timeline
- Quick wins you can deliver in first 30 days
- Request for approval and support

Step 2.4: Implement Quick Wins (4-6 hours)

Build momentum with some quick wins you can deliver this week:

Quick Win #1: Document Termination Checklist (1 hour)

Create a simple checklist for removing access when someone leaves:

TERMINATION ACCESS REMOVAL CHECKLIST

Employee: ___________________  Last Day: ___________

Completed by: _______________ Date: ______________

[ ] Disable Active Directory account
[ ] Disable email
[ ] Disable VPN
[ ] Remove from [System 1]
[ ] Remove from [System 2]
[ ] Remove from [System 3]
[ ] Collect laptop
[ ] Collect phone
[ ] Collect badge/keys
[ ] Change passwords on shared accounts they knew
[ ] Confirm all access removed

Notes: _________________________________________

Share with HR and managers. Use it immediately.

Quick Win #2: Enable MFA on Email (2-3 hours)

If you haven't already, enable MFA on your email system. This prevents 99% of account takeovers.

For Microsoft 365:1. Go to Azure AD admin center
2. Navigate to Security > MFA
3. Enable for all users (or start with admins/remote users)
4. Choose allowed methods (authenticator app, SMS, phone call)
5. Communicate to users with setup instructions
6. Set grace period (7-14 days) for enrollment

For Google Workspace:1. Go to Admin console
2. Security > Authentication > 2-Step Verification
3. Choose "Allow users to turn on 2-Step Verification"
4. Consider "Enforcement" for admins first
5. Provide user setup guide

Quick Win #3: Create Access Request Form (1 hour)

Create a simple form (Google Form, Microsoft Form, or ServiceNow ticket template):

Access Request Form Fields:- Requestor name and email
- Employee name (who needs access)
- System/application name
- Type of access needed (read-only, edit, admin)
- Business justification
- Temporary or permanent
- If temporary, end date
- Manager approval (signature or email confirmation)
- Date submitted
- Date approved
- Date access granted

Quick Win #4: Update Password Requirements (1 hour)

Update password policy in your systems to require:
- Minimum 12 characters
- Complexity OR passphrase option
- No common passwords (password123, company name)
- Account lockout after 6 failed attempts

Most systems:Active Directory Group Policy, Azure AD Password Policy, or application-specific settings.

Deliverable:Implementation roadmap, approved budget, quick wins completed and communicated

## Phase 2: Core Access Controls (Weeks 3-6)

### Week 3: Access Request Process

Goal:Formalize how people request and receive access.

Step 3.1: Define Approval Matrix (3-4 hours)

Document who can approve what level of access.

Sample Approval Matrix:

| Access Type | Approver(s) | SLA |
| --- | --- | --- |
| Standard applications (new hire) | Hiring Manager | 1 business day |
| Department-specific applications | Department Manager | 2 business days |
| Sensitive data access | Manager + IT Manager | 3 business days |
| Administrative/privileged access | Manager + IT Manager + CISO | 5 business days |
| Contractor/temporary access | Sponsor + Manager | 2 business days |
| Emergency access | On-call IT Manager | 4 hours (formalize next day) |

Step 3.2: Implement Access Request Workflow (4-6 hours)

Set up formal workflow for access requests:

Option 1: Simple (Email-based):- Use the form you created in Quick Wins
- Manager sends approval via email
- IT provisions access
- IT confirms completion via email
- All emails saved for audit trail

Option 2: Ticketing System:- Create access request ticket type in your IT ticketing system
- Route for approval based on access type
- IT fulfills when approved
- Ticket serves as audit record

Option 3: Automated (IAM Platform):- Configure access request workflow in identity management tool
- Users request via self-service portal
- Automatic routing to appropriate approver
- Optional auto-provisioning for standard access
- Complete audit trail in system

Step 3.3: Create Role Definitions (5-7 hours)

Define standard roles and their associated access to make provisioning consistent.

Sample role template:

ROLE: Sales Representative

Systems Access:
- Email (standard mailbox)
- CRM (Salesforce - read/write)
- File share (Sales folder - read/write, Company folder - read only)
- Communication tools (Slack, Zoom)
- Sales tools (LinkedIn Sales Navigator, DocuSign)

Data Access:
- Customer contact information
- Sales pipeline data
- Marketing materials
- Price lists

Typical Users: Sales team members
Approved by: Sales Manager
Reviewed: Annually

Common roles to define:- Standard employee
- Manager
- Executive
- Finance/accounting
- IT support
- IT administrator
- Contractor
- Department-specific roles

Step 3.4: Document and Train (2-3 hours)

Create simple documentation:
- One-page "How to Request Access" guide for employees
- One-page "How to Approve Access" guide for managers
- Detailed "Access Provisioning Procedures" for IT team

Present to managers in a 30-minute meeting. Answer questions. Get buy-in.

### Week 4-5: User Lifecycle Management

Goal:Automate or systematize onboarding, changes, and offboarding.

Step 4.1: New Hire Access Provisioning (6-8 hours)

Create standardized onboarding checklist:

NEW HIRE ACCESS CHECKLIST

Name: _________________  Start Date: __________
Department: ____________  Manager: ___________

PRE-START (1 week before):
[ ] Create Active Directory account
[ ] Create email mailbox
[ ] Assign to appropriate security groups
[ ] Provision standard applications (based on role)
[ ] Order hardware (laptop, phone)
[ ] Create badge

DAY 1:
[ ] Provide credentials (temporary password)
[ ] User changes password
[ ] Set up MFA
[ ] Complete security awareness training
[ ] Review acceptable use policy

WEEK 1:
[ ] Request department-specific access
[ ] Provision approved systems
[ ] Verify all access working
[ ] Schedule follow-up check

Notes: ______________________________________

Coordinate with HR:- HR notifies IT of new hires 1-2 weeks in advance
- HR provides: name, role, department, start date, manager
- IT uses this info to prepare accounts
- Day 1 is smooth because everything is ready

Step 4.2: Role Changes and Transfers (4-5 hours)

Process for internal role changes:

Manager notifies IT of change

Employee name

New role/department

Effective date

Manager confirmation

IT reviews current access

Document what they have today

Identify what they should have in new role

IT makes adjustments

Remove access no longer needed

Add access required for new role

Update security group memberships

Update email distribution lists

IT confirms with employee and manager

Manager confirmation

IT reviews current access

Identify what they should have in new role

IT makes adjustments

Update email distribution lists

IT confirms with employee and manager

Timeline:Complete within 1-2 business days of role change

Step 4.3: Termination/Offboarding Process (5-7 hours)

Enhance the termination checklist from Phase 1:

For planned departures (resignation):- HR notifies IT when resignation received
- IT prepares but doesn't execute until last day
- Manager ensures knowledge transfer while employee still has access
- Last day: IT executes termination checklist
- Access removed by end of business day

For immediate terminations:- HR notifies IT before termination meeting
- IT disables critical access during meeting
- Complete removal within 2 hours
- Prioritize: VPN, email, remote access, sensitive systems

Automated reminders:Set up automated checks:
- Contractors: Review access 2 weeks before contract end
- Temporary access: Automatic expiration reminders
- Long-term disabled accounts: Delete after 90 days

Step 4.4: Implement Access Monitoring (6-8 hours)

Set up basic monitoring for:

Failed login attempts:- Alert after 3 failed attempts on privileged accounts
- Alert after 10 failed attempts on standard accounts
- Daily report of all account lockouts

After-hours access:- Weekly report of weekend/night access to sensitive systems
- Flag unusual access patterns

Privileged account usage:- Log all administrative actions
- Weekly review of admin account activity
- Alert on privilege escalation

Tools:- Built-in logging (Windows Event Logs, Azure AD sign-in logs, application logs)
- SIEM if you have one
- Simple scripts to aggregate and alert
- Weekly manual review if no automation yet

### Week 6: Access Reviews

Goal:Implement regular review of who has access to what.

Step 6.1: Design Access Review Process (3-4 hours)

Determine review frequency:- All users: Annual review
- Privileged/admin access: Quarterly review
- Contractors: Quarterly review
- Sensitive data access: Semi-annual review

Create review process:

IT generates access reports

List of users and their access by system

Focus on: privileged accounts, sensitive data, inactive accounts

Send to appropriate reviewers

System owners review their systems

Managers review their team members

IT reviews privileged accounts

Reviewers certify or request changes

Confirm still needed: Approve

No longer needed: Request removal

Unsure: Investigate with employee

IT implements changes

Remove access marked for removal

Document review completion

Save evidence for auditors

Follow up on late reviews

Send reminders at 7 days, 14 days

Escalate to leadership if needed

Focus on: privileged accounts, sensitive data, inactive accounts

Send to appropriate reviewers

IT reviews privileged accounts

Reviewers certify or request changes

Unsure: Investigate with employee

IT implements changes

Save evidence for auditors

Follow up on late reviews

Step 6.2: Create Review Templates (2-3 hours)

Simple review spreadsheet:

| Employee | System | Access Level | Still Needed? | Reviewer | Date |
| --- | --- | --- | --- | --- | --- |
| John Smith | Salesforce | Admin | YES / NO | Sales Manager |  |
| Jane Doe | QuickBooks | Standard | YES / NO | CFO |  |

Instructions for reviewers:- Review each person's access
- Confirm they still need it for current role
- Mark YES or NO
- If NO, we'll remove access
- If unsure, investigate before approving
- Return within 2 weeks

Step 6.3: Conduct First Access Review (8-10 hours)

Execute your first review:

Generate current access reports(2-3 hours)

Export user lists from each system

Combine into review spreadsheets

Identify reviewers for each area

Send for review (1 hour)

Email reviews to managers/system owners

Provide clear instructions and deadline

Offer to answer questions

Monitor and remind (2-3 hours over 2 weeks)

Track completion

Send reminders

Answer questions

Escalate delays

Implement changes (3-4 hours)

Remove access marked for removal

Update access lists

Notify affected users

Document completion

Save completed reviews

Document any findings or patterns

Note improvements for next time

Identify reviewers for each area

Send for review(1 hour)

Offer to answer questions

Monitor and remind(2-3 hours over 2 weeks)

Escalate delays

Implement changes(3-4 hours)

Notify affected users

Document completion

Common findings in first review:- 10-20% of access can be removed (no longer needed)
- Ex-employees still have access (fix immediately!)
- Shared accounts discovered (plan to eliminate)
- Inconsistent access across similar roles

Deliverable:Completed access review, evidence saved, improvements identified

## Phase 3: Authentication and Security (Weeks 7-10)

### Week 7-8: Multi-Factor Authentication

Goal:Deploy MFA across your critical systems.

Step 7.1: MFA Deployment Plan (2-3 hours)

Prioritize MFA rollout:

Phase 1 (Already done in Quick Wins):- Email

Phase 2 (This week):- VPN / Remote access
- Cloud applications (Microsoft 365, Google Workspace, AWS, Azure)
- Administrator accounts (always require MFA)

Phase 3 (Next 2-4 weeks):- Systems with sensitive data (HR, finance, customer data)
- Source code repositories
- Critical business applications

Phase 4 (Following months):- All remaining systems where technically feasible

Step 7.2: Choose MFA Methods (1-2 hours)

Recommended method priority:1.Hardware security keys(FIDO2) - for admins and high-risk users
2.Authenticator apps(Microsoft/Google Authenticator, Authy) - for all users
3.Push notifications- convenient for mobile users
4.SMS- acceptable as backup only
5.Email codes- not recommended except for low-risk systems

Purchase considerations:- Hardware keys: $20-50 per key, buy 2 per user (backup)
- Authenticator apps: Free
- SMS: Often included in MFA platforms, or $0.02-0.05 per message

Step 7.3: Deploy MFA to Priority Systems (15-20 hours)

For each system:

Configure MFA(2-3 hours per system)

Enable MFA in admin settings

Choose allowed methods

Configure registration policies

Set up bypass/emergency codes

Pilot with IT team (1-2 hours)

IT team enables MFA first

Work through any issues

Document setup process

Create user guide

Communicate to users (1-2 hours)

Announce MFA rollout 2 weeks ahead

Explain why (security, compliance)

Provide setup instructions

Offer support options

Set enrollment deadline

Enrollment period (2-3 weeks)

Users enroll at their own pace

Provide help desk support

Track enrollment progress

Send reminders

Enforcement (after enrollment period)

MFA becomes required

Users can't log in without MFA

Help desk handles stragglers

Document completion

Set up bypass/emergency codes

Pilot with IT team(1-2 hours)

Create user guide

Communicate to users(1-2 hours)

Set enrollment deadline

Enrollment period(2-3 weeks)

Send reminders

Enforcement(after enrollment period)

Sample communication:

Subject: Important: Multi-Factor Authentication (MFA) Coming to [System]

Starting [Date], you'll need to use multi-factor authentication to access [System].

What is MFA?
MFA adds an extra security layer beyond your password. You'll enter your password, then confirm your identity using your phone.

Why are we doing this?
MFA prevents 99% of account takeover attacks. It's an industry best practice and required for our security compliance.

What you need to do:
1. Download authenticator app (Microsoft Authenticator, Google Authenticator, or Authy)
2. Enroll your device by [Deadline]
3. Use MFA every time you log in

Need help?
- Setup guide: [Link]
- Video tutorial: [Link]
- Help desk: [Contact info]

Thank you for helping keep our systems secure!

Step 7.4: Monitor and Support (Ongoing)

Track metrics:- MFA enrollment rate
- Help desk tickets related to MFA
- Failed MFA attempts
- Users locked out due to MFA issues

Provide support:- Clear documentation and guides
- Responsive help desk
- Backup methods for users who lose devices
- Emergency bypass for critical situations

### Week 9: Password Management

Goal:Enhance password security across your organization.

Step 9.1: Implement Password Manager (5-7 hours)

Choose enterprise password manager:- LastPass Enterprise
- 1Password Business
- Bitwarden Enterprise
- Dashlane Business

Typical cost:$4-8 per user/month

Deployment:1. Purchase licenses
2. Configure organizational policies
3. Create groups and sharing policies
4. Deploy to pilot group (IT team)
5. Create user guides
6. Communicate to organization
7. Provide training and support
8. Track adoption

Benefits:- Users can have unique passwords everywhere
- Reduces password resets
- Enables complexity without pain
- Secure password sharing when needed
- Audit trail of access

Step 9.2: Harden Password Policies (3-4 hours)

Review and update password requirements:

Standard users:- 12+ characters (or 16+ if no MFA)
- Complexity or passphrase
- No password expiration if MFA enabled
- 90-day expiration if no MFA
- Cannot reuse last 5 passwords
- Account lockout after 6 failed attempts

Administrators:- 16+ characters
- Complexity required
- 60-90 day expiration (even with MFA)
- Cannot reuse last 10 passwords
- Separate admin account from standard account

Implement in:- Active Directory Group Policy
- Azure AD Password Policy
- Application-specific settings where available

Step 9.3: Credential Breach Monitoring (2-3 hours)

Set up monitoring for breached passwords:

Options:- Azure AD Password Protection (checks against known breached passwords)
- Have I Been Pwned Enterprise API
- Commercial identity protection services

Process:- Monitor for compromised credentials
- Alert affected users to change passwords
- Force reset if high risk
- Track and investigate patterns

### Week 10: Privileged Access Management

Goal:Enhance controls around administrative and privileged accounts.

Step 10.1: Inventory Privileged Access (4-5 hours)

Identify all privileged accounts:- Windows domain admins
- Azure/AWS admin accounts
- Database administrators
- Application administrators
- Security tool admins
- Network equipment admins
- Any account that can change system settings or access all data

Document for each:- Account name
- Who uses it
- What systems it can access
- How often it's used
- Password stored where
- MFA enabled?
- Logging enabled?

Step 10.2: Implement PAM Best Practices (8-12 hours)

For organizations not ready for full PAM platform:

1. Separate Admin Accounts (2-3 hours)- Admins have two accounts: standard + admin
- Standard account for email, web, daily work
- Admin account only for administrative tasks
- Name convention: john.smith (standard) + john.smith-admin (admin)

2. Enhanced Admin Requirements (1-2 hours)- Require MFA for all admin accounts (no exceptions)
- Longer passwords (16+ characters)
- More frequent password changes
- No email on admin accounts
- No web browsing from admin accounts

3. Admin Workstations (3-4 hours)- Dedicated admin workstations or jump boxes
- No internet access or email
- Only admin tools installed
- Enhanced logging
- Restricted physical access

4. Just-in-Time Admin Access (2-3 hours)- Remove standing admin privileges where possible
- Use time-limited elevation
- Request-approval-use-remove workflow
- Tools: Azure AD PIM, native Windows/Linux tools

5. Privileged Session Recording (2-3 hours)- Log all admin session activity
- Record admin actions where possible
- Regular review of admin activity
- Alert on suspicious admin behavior

For organizations ready for PAM platform:- Evaluate solutions: CyberArk, BeyondTrust, Thycotic, Delinea
- Budget: $10,000-100,000+ depending on size and features
- Implementation: 3-6 months with vendor support
- Benefits: Automated password rotation, session recording, just-in-time access, audit trails

Step 10.3: Admin Activity Monitoring (3-4 hours)

Set up monitoring:- All admin logins logged
- Privilege escalation logged
- Administrative changes logged
- Weekly review of admin activity
- Alerts for suspicious patterns

Review process:- Designated reviewer (Security Lead, CISO)
- Weekly review of admin logs
- Investigate anomalies
- Document review completion

## Phase 4: Advanced Controls and Optimization (Weeks 11-14)

### Week 11-12: Identity Management Enhancement

Goal:Implement centralized identity management if not already in place.

Step 11.1: Evaluate Identity Platforms (3-5 hours)

If you don't have centralized identity management:

Options:-Azure Active Directory- Best for Microsoft-heavy environments
-Okta- Best of breed, works with everything
-Google Workspace- Good for Google-centric orgs
-JumpCloud- Good for small-medium businesses
-OneLogin- Mid-market focused

Cost:$3-12 per user/month depending on features

Key features needed:- Single Sign-On (SSO)
- MFA platform
- User provisioning/deprovisioning
- Access governance
- Reporting and analytics
- Integration with your applications

Step 11.2: Implement SSO (15-25 hours)

Single Sign-On implementation:

Identify SSO-capable applications(3-4 hours)

Review your application inventory

Check which support SAML, OAuth, or OIDC

Prioritize most-used applications

Document integration complexity

Configure identity provider (2-3 hours)

Set up base configuration

Create user groups

Configure authentication policies

Set up MFA requirements

Integrate applications (2-4 hours per app)

Configure SSO in application

Configure in identity provider

Test with pilot users

Document configuration

Train users on new login flow

Rollout SSO (2-3 hours per app)

Communicate changes to users

Provide updated login instructions

Support users through transition

Monitor for issues

Document integration complexity

Configure identity provider(2-3 hours)

Set up MFA requirements

Integrate applications(2-4 hours per app)

Train users on new login flow

Rollout SSO(2-3 hours per app)

Benefits:- Users remember one password instead of dozens
- Reduced password resets
- Faster onboarding/offboarding
- Better security (MFA at single point)
- Improved audit trail

Step 11.3: Automate Provisioning (10-15 hours)

Set up automated user provisioning:

SCIM (System for Cross-domain Identity Management):- Automatic account creation when user added to directory
- Automatic account deletion when user removed
- Automatic updates when user info changes
- Reduces manual IT work
- Reduces delays
- Reduces errors

Implementation:1. Identify applications supporting SCIM
2. Configure provisioning in identity platform
3. Map attributes (name, email, department, role)
4. Set up provisioning rules
5. Test thoroughly
6. Enable for production

Applications to prioritize:- SaaS applications you use frequently
- Applications requiring quick access provisioning
- Applications with many user changes

### Week 13: Access Analytics and Reporting

Goal:Implement analytics to understand and improve access patterns.

Step 13.1: Define Key Metrics (2-3 hours)

Track these access control KPIs:

Operational metrics:- Average time to provision new access: [X] hours/days
- Average time to remove access on termination: [X] hours
- Access request backlog: [X] pending requests
- Password reset requests per month: [X]
- Account lockouts per week: [X]

Security metrics:- % of users with MFA enabled: [X]%
- % of privileged accounts with MFA: [X]%
- Failed login attempts per day: [X]
- After-hours access events per week: [X]
- Accounts inactive > 90 days: [X]

Compliance metrics:- % of access reviews completed on time: [X]%
- % of users with current access review: [X]%
- % of systems with access logging: [X]%
- Access violations identified: [X]
- Time to remediate violations: [X] days

Step 13.2: Create Dashboards (5-7 hours)

Build reporting dashboards:

Option 1: Manual (spreadsheet-based)- Excel or Google Sheets
- Updated weekly or monthly
- Shared with leadership
- Simple charts and graphs

Option 2: Automated (BI tool)- Power BI, Tableau, or similar
- Real-time or daily refresh
- Interactive dashboards
- Drill-down capability

Key reports to create:1.Access Provisioning Report- New access requests, timing, backlogs
2.Termination Report- How quickly access removed after terminations
3.MFA Adoption Report- MFA enrollment and usage rates
4.Access Review Status- Review completion and findings
5.Security Events Report- Failed logins, after-hours access, violations
6.Privileged Access Report- Admin account usage and monitoring

Step 13.3: Establish Review Cadence (1-2 hours)

Regular review meetings:

Weekly:IT team reviews operational metrics and addresses issues

Monthly:Leadership reviews security and compliance metrics

Quarterly:Executive summary of access control program health

Annually:Comprehensive program review and planning

### Week 14: Documentation and Training

Goal:Complete documentation and train your organization.

Step 14.1: Finalize Policy Documentation (6-8 hours)

Complete your access control policy:- Incorporate all processes you've implemented
- Add organizational specifics
- Reference actual tools and systems you're using
- Review and approve with leadership
- Publish and communicate

Step 14.2: Create User Training (8-10 hours)

Develop training materials:

Access Control 101 (30 minutes, all users)- Why access control matters
- Password and MFA best practices
- How to request access
- Responsibilities for protecting credentials
- What to do if something goes wrong

Manager Training (45 minutes)- How to request access for team members
- Approving access requests
- Access reviews
- Termination procedures
- Manager responsibilities

IT Admin Training (2 hours)- Access provisioning procedures
- Using IAM tools
- Monitoring and logging
- Investigating security events
- Audit and compliance requirements

Delivery methods:- In-person or video training sessions
- Recorded videos for on-demand viewing
- Written quick reference guides
- Integration into onboarding

Step 14.3: Create Audit Evidence Package (4-5 hours)

Prepare evidence for auditors:

Policy and procedures:- Access Control Policy (approved and dated)
- Access request procedures
- Termination procedures
- Access review procedures
- Privileged access management procedures

Evidence of implementation:- Access review reports (last 4 quarters)
- Sample access request approvals
- Termination checklists (samples)
- MFA enrollment reports
- Privileged access monitoring logs
- Security awareness training completion

Technical configuration documentation:- Password policy settings
- MFA configuration
- Account lockout settings
- Logging and monitoring configuration
- SSO integration documentation

Store in organized folder structure:

/Access-Control-Evidence
  /Policies
  /Procedures
  /Access-Reviews
  /Access-Requests
  /Terminations
  /MFA-Reports
  /Training-Records
  /Technical-Configuration
  /Monitoring-Logs

## Phase 5: Ongoing Operations and Continuous Improvement

Goal:Maintain your access control program and continuously improve.

### Ongoing Activities

Daily:- Monitor failed login attempts and security alerts
- Process urgent access requests
- Respond to help desk tickets

Weekly:- Process standard access requests
- Review privileged access activity
- Review security monitoring reports
- Update KPI dashboard

Monthly:- Review access control metrics with leadership
- Process standard access modifications
- Review and update role definitions as needed
- Test backup authentication methods

Quarterly:- Conduct privileged access reviews
- Conduct contractor access reviews
- Review and update procedures based on lessons learned
- Test emergency access procedures
- Vulnerability assessment of IAM systems

Semi-annually:- Conduct sensitive data access reviews
- Review and test disaster recovery for IAM systems
- Comprehensive security assessment

Annually:- Conduct comprehensive access review for all users
- Review and update Access Control Policy
- Leadership review of program effectiveness
- Budget planning for next year
- Vendor reviews (IAM platform, PAM, password manager)
- Staff training and certification updates

### Continuous Improvement

Collect feedback:- User satisfaction with access processes
- IT team feedback on operational efficiency
- Manager input on access approval process
- Auditor feedback on controls and evidence

Monitor industry trends:- New authentication technologies
- Emerging threats
- Regulatory changes
- Best practice evolution

Regular optimization:- Automate manual processes
- Streamline approval workflows
- Enhance monitoring and alerting
- Improve reporting and analytics
- Expand SSO coverage

Measure success:- Reduced time to provision access
- Reduced password reset requests (SSO adoption)
- Increased MFA adoption
- Clean access reviews (less unnecessary access)
- Fewer security incidents
- Positive audit findings
- User satisfaction

## Troubleshooting Common Challenges

### Challenge 1: Resistance to MFA

Symptoms:- Users complain MFA is inconvenient
- Low enrollment rates
- Users looking for workarounds

Solutions:- Emphasize security benefits (prevents 99% of attacks)
- Make it as easy as possible (authenticator app, not SMS)
- Executive leadership must use it and endorse it
- No exceptions (even for executives)
- Provide excellent support during rollout
- Consider: "No MFA = no remote access" policy

### Challenge 2: Access Request Backlog

Symptoms:- Access requests taking too long
- IT overwhelmed with requests
- Business complaining about delays

Solutions:- Implement role-based provisioning (most access automatic)
- Use SSO with automatic provisioning where possible
- Set clear SLAs and measure them
- Escalation path for urgent requests
- Get more IT resources if truly overwhelmed
- Self-service access for appropriate systems

### Challenge 3: Incomplete Terminations

Symptoms:- Ex-employees still have access to some systems
- Auditor findings on improper access removal
- Termination checklist not consistently followed

Solutions:- Automate where possible (disable AD = disable many things)
- Maintain accurate system inventory
- Mandatory HR notification process
- IT verifies completion, not just checklist
- Monthly audit of disabled accounts still having access
- Consequences for managers who don't notify promptly

### Challenge 4: Failed Access Reviews

Symptoms:- Managers don't complete reviews on time
- Reviews are rubber-stamped without real verification
- No one wants to remove access

Solutions:- Make reviews easy (simple format, clear instructions)
- Set expectations: this is a manager responsibility
- Executive support and communication
- Escalate incomplete reviews to leadership
- Recognize and thank managers who complete reviews thoroughly
- Show value: "We removed 50 unnecessary accounts, improving security"

### Challenge 5: Shared Accounts

Symptoms:- Multiple people using same credentials
- Can't trace actions to individuals
- Auditor concerns about accountability

Solutions:- Create individual accounts for everyone
- Use access groups/roles, not shared accounts
- For truly necessary shared accounts (rare):
  - Document who has access
  - Change password when anyone with access leaves
  - Enhanced monitoring
  - Limit what shared account can do
- Work toward eliminating all shared accounts

### Challenge 6: Shadow IT

Symptoms:- Departments using apps IT doesn't know about
- No access control on these systems
- Compliance and security gaps

Solutions:- Discover shadow IT (cloud access security broker, network monitoring)
- Don't punish, understand why (IT too slow? Missing capability?)
- Bring shadow IT into IAM fold
- Create process for evaluating and approving new tools
- IT becomes enabler, not blocker
- Regular cloud application discovery scans

### Challenge 7: Budget Constraints

Symptoms:- Can't afford enterprise IAM platform
- Can't staff adequately
- Manual processes everywhere

Solutions:- Start with free/low-cost tools (Azure AD Free, Google Workspace, JumpCloud)
- Prioritize: MFA first, SSO second, automation third
- Phase implementation over multiple budget cycles
- Calculate ROI (reduced password resets, faster provisioning, prevented breaches)
- Present business case to leadership
- Consider managed services to supplement staff

## Success Criteria

You've successfully implemented access control when:

Minimum viable program:- [ ] All new hire access follows documented process
- [ ] All terminations follow documented checklist
- [ ] MFA enabled on email and remote access
- [ ] Strong password policy enforced
- [ ] Quarterly privileged access review completed
- [ ] Annual access review completed for all users
- [ ] Logging enabled on critical systems
- [ ] Basic monitoring in place
- [ ] Can produce evidence for auditors

Mature program:- [ ] Centralized identity management (Azure AD, Okta, etc.)
- [ ] SSO for 80%+ of applications
- [ ] MFA for 100% of users on all critical systems
- [ ] Automated provisioning/deprovisioning
- [ ] Role-based access control implemented
- [ ] Privileged access management platform
- [ ] Real-time monitoring and alerting
- [ ] Self-service password reset and access requests
- [ ] Metrics-driven continuous improvement
- [ ] Clean audits with no access control findings

Congratulations on implementing your access control program! Regular review and continuous improvement will keep your program effective as your organization grows and changes.