| Policy Owner: | Chief Operating Officer / Operations Manager |
| --- | --- |
| Effective Date: | January 1, 2025 |
| Version: | 1.0 |
| Classification: | Internal Use Only |

# Business Resilience and Recovery Plan Implementation Workbook

Implementation Workbook

# Business Resilience and Recovery Plan Implementation Workbook

## How to Use This Workbook

This workbook guides you through building a comprehensive Business Resilience and Recovery Program from the ground up. Whether you're starting from scratch or improving an existing program, this workbook provides practical steps, templates, and guidance.

What's included:- Business Impact Analysis (BIA) methodology and execution
- Risk assessment for BC/DR threats
- Developing continuity and recovery strategies
- Writing recovery procedures
- Crisis communication planning
- Building a testing program
- Budget planning and resource allocation

Timeline:3-6 months for initial program implementation (varies by organization size and complexity)

Who should use this:Operations managers, business continuity managers, IT managers, COOs, and anyone responsible for implementing or improving business resilience capabilities.

Phases of implementation:-Phase 1 (Weeks 1-4):Assessment and planning - BIA, risk assessment, strategy development
-Phase 2 (Weeks 5-10):Documentation - Write plans, procedures, communication templates
-Phase 3 (Weeks 11-12):Testing - Initial testing and refinement
-Ongoing:Maintenance, annual testing, continuous improvement

## Section 1: Business Impact Analysis (BIA) (8-10 pages → 9 pages)

### Why BIA Matters

The Business Impact Analysis is the foundation of your entire BC/DR program. Without understanding what's critical and the impact of disruptions, you're planning in the dark.

BIA tells you:- What business functions are critical (must recover first)
- How long you can be down before unacceptable damage (MTD)
- How quickly you must recover (RTO)
- How much data you can lose (RPO)
- What resources you need to recover
- Dependencies between functions and systems

BIA drives everything else:- Recovery priorities
- Investment decisions (what to spend money protecting)
- Strategy selection (what recovery strategies needed)
- Testing priorities

### Step 1.1: Prepare for BIA (Week 1)

Preparation activities:

1. Secure executive sponsorship:- BIA requires time from busy executives and department heads
- Get CEO/Owner commitment
- Communicate importance to leadership
- Schedule dedicated time for interviews/workshops

2. Identify stakeholders:- Department heads for each business unit
- IT leadership for technology perspective
- Finance for financial impact assessment
- Key process owners
- Compliance/legal if applicable

3. Choose BIA approach:

For SMBs (<50 employees):- Lightweight approach: 1-day workshop with all key stakeholders
- Use questionnaire to gather initial data
- Follow-up interviews if needed
- Document in spreadsheet
- Timeline: 1-2 weeks total

For larger organizations (50+ employees):- Formal approach: Individual interviews with each department head
- Detailed questionnaires sent in advance
- Follow-up analysis and validation
- Professional BIA software or detailed spreadsheet
- Timeline: 3-4 weeks

4. Prepare BIA materials:- Interview questions/questionnaire
- BIA template/spreadsheet
- Calendar invites for interviews/workshops
- Explanation of BIA purpose and terms (RTO, RPO, MTD)

### Step 1.2: Identify Business Functions (Week 1-2)

Goal:Create comprehensive inventory of all business functions/processes.

Process:

1. Start with high-level functions:

Common business functions (customize for your organization):
- Sales and marketing
- Order processing
- Customer service/support
- Product delivery/fulfillment
- Manufacturing/production
- Finance and accounting
- Payroll
- Human resources
- IT operations
- Facilities management

2. Break down into specific processes:

For each function, identify specific processes. Example:

Finance and Accounting:- Accounts receivable (invoicing customers, collecting payments)
- Accounts payable (paying vendors and suppliers)
- Payroll processing
- Financial reporting
- Banking and treasury operations
- Expense management

3. Document each process:

For each process, capture:
- Process name and description
- Department/owner
- Key personnel required
- Technology systems used
- Peak times/seasonal considerations
- Regulatory/compliance requirements
- Contractual obligations (SLAs with customers)

BIA Process Inventory Template:

| Process ID | Process Name | Description | Owner | Dept | Systems Used | Staff Required | Peak Times | Compliance Reqs |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FIN-001 | Invoicing | Generate and send customer invoices | Jane Smith | Finance | QuickBooks, ERP | 2 | Month-end | SOC 2, Tax |
| CS-001 | Customer Support | Answer customer questions, troubleshoot | Bob Jones | Support | Zendesk, Phone | 5 | Business hours | SLA - 24hr response |

Tip:Start broad, refine later. Better to identify 20-30 major processes than get lost in minutiae of 200 sub-processes.

### Step 1.3: Assess Impact of Disruption (Week 2)

Goal:Quantify the impact if each process is disrupted.

Impact categories:

1. Financial Impact:-Revenue loss:How much revenue lost per hour/day if this process down?
-Recovery costs:Cost to restore this process
-Fines/penalties:Regulatory fines or contractual penalties for non-performance
-Extra expenses:Overtime, expedited shipping, temporary staff, etc.

Quantification approach:- Calculate hourly/daily revenue for revenue-generating processes
- Estimate fines for compliance-related processes
- Project recovery costs (staff time, vendor costs, etc.)

Example:- Order processing down = $10,000/hour in lost sales
- Payroll system down at payroll time = Potential compliance violations, employee dissatisfaction (hard to quantify but significant)

2. Operational Impact:- Productivity loss (staff idle, can't do jobs)
- Service degradation (slower, manual workarounds)
- Cascading effects (other processes that depend on this one)
- Backlog that must be cleared after recovery

3. Reputational Impact:- Customer dissatisfaction and potential loss
- Damage to brand and reputation
- Negative media coverage
- Social media complaints
- Long-term customer relationship impact

Scale:Low / Medium / High / Critical

4. Compliance/Legal Impact:- Regulatory violations
- Contractual breaches (SLA violations)
- Legal liability
- Reporting requirements

Scale:None / Minor / Moderate / Severe

Impact over time:

Impact typically increases the longer the outage. Assess impact at multiple time intervals:

| Time Interval | Financial Impact | Operational Impact | Reputational Impact | Compliance Impact |
| --- | --- | --- | --- | --- |
| 1 hour | $10K revenue loss | Minor - workarounds exist | None | None |
| 4 hours | $40K revenue loss | Moderate - backlog building | Low - few complaints | None |
| 8 hours | $80K revenue loss | Significant - major backlog | Medium - complaints mounting | Minor |
| 24 hours | $200K revenue loss | Severe - can't fulfill orders | High - customer loss | Moderate - SLA breach |
| 3 days | $600K revenue loss | Critical - losing customers | Critical - brand damage | Severe - regulatory |
| 1 week | $1.4M revenue loss | Catastrophic | Catastrophic | Severe |

Interview questions for impact assessment:

Ask department heads:
1. "If this process stopped completely, what would happen in the first hour? First 4 hours? First day? First week?"
2. "What's the financial impact (revenue loss, costs) per hour/day?"
3. "At what point does the impact become unacceptable or catastrophic?"
4. "What compliance or contractual obligations do we have related to this process?"
5. "What happens to customers if this process is unavailable?"
6. "What other processes depend on this process?"

### Step 1.4: Determine Recovery Objectives (Week 2-3)

Goal:Establish RTO, RPO, and MTD for each critical process.

Key metrics:

Maximum Tolerable Downtime (MTD):- The longest time a process can be unavailable before causing unacceptable damage
- Based on impact assessment: When does impact become catastrophic?
- Example: Order processing MTD = 8 hours (beyond this, lose too many customers)

Recovery Time Objective (RTO):- Target time to restore the process after disruption
- Must be less than MTD (need buffer for unexpected issues)
- Example: Order processing RTO = 4 hours (gives 4-hour buffer before MTD)

Recovery Point Objective (RPO):- Maximum acceptable data loss measured in time
- Based on: How often does data change? How much data loss can we tolerate?
- Example: Order processing RPO = 1 hour (can't lose more than 1 hour of orders)

Relationship:

Disruption occurs → Recover within RTO → Before reaching MTD
                  → Restore data to within RPO of disruption

RTO/RPO determination process:

1. Review impact assessment:- Identify when impact becomes unacceptable (this suggests MTD)
- Consider cumulative impact over time

2. Classify processes by criticality:

Tier 1 - Critical (Mission-Critical):- Must recover immediately
- MTD: 4-8 hours
- RTO: 2-4 hours
- RPO: 15 minutes to 1 hour
- Examples: Order processing, payment processing, critical customer-facing systems

Tier 2 - Important (Business-Critical):- Must recover within 1-2 days
- MTD: 24-48 hours
- RTO: 8-24 hours
- RPO: 4-24 hours
- Examples: Accounting, reporting, internal communications

Tier 3 - Standard (Non-Critical):- Can recover within a week
- MTD: 1 week
- RTO: 2-5 days
- RPO: 24-48 hours
- Examples: Marketing, HR processes, training

Tier 4 - Low Priority:- Can recover when convenient
- MTD: >1 week
- RTO: >1 week
- RPO: Days to weeks
- Examples: Archived data, non-essential reporting

3. Validate with stakeholders:- Review proposed RTO/RPO with process owners
- Confirm realistic and necessary
- Balance between ideal and achievable/affordable

4. Document in BIA:

| Process | Criticality Tier | MTD | RTO | RPO | Justification |
| --- | --- | --- | --- | --- | --- |
| Order Processing | Tier 1 | 8 hrs | 4 hrs | 1 hr | Revenue loss $10K/hr; customer loss after 8 hrs |
| Customer Support | Tier 1 | 8 hrs | 4 hrs | 24 hrs | SLA requires 24hr response; brand impact |
| Accounting | Tier 2 | 3 days | 2 days | 24 hrs | Can delay for 72hrs; month-end critical |

### Step 1.5: Identify Dependencies and Resources (Week 3)

Goal:Understand what each process needs to operate.

Dependencies to identify:

1. Technology dependencies:- IT systems and applications required
- Network and infrastructure
- Cloud services
- Hardware (servers, workstations, phones)
- Integrations between systems

Example:- Order Processing depends on: ERP system, inventory system, payment gateway, email, customer database

2. Personnel dependencies:- How many staff required (minimum and full capacity)
- Required skills and knowledge
- Key person dependencies (can only one person do this?)
- Ability to work remotely

Example:- Order Processing requires: Minimum 2 staff (4 for full capacity), basic computer skills, order entry training, can work remotely

3. Facility dependencies:- Physical space requirements
- Equipment and machinery
- Environmental requirements (temperature, humidity, etc.)
- Accessibility requirements

Example:- Manufacturing requires: Factory floor, machinery, raw materials, power, climate control - cannot work remotely

4. Vendor/supplier dependencies:- Critical vendors and suppliers
- External service dependencies
- Supply chain dependencies
- Communication service providers (internet, phone)

Example:- Order Processing depends on: Internet provider, payment processor (Stripe), shipping carriers (UPS, FedEx), raw material suppliers

5. Information/data dependencies:- Data required to operate process
- Reports and documentation
- Communication channels

Example:- Order Processing requires: Customer database, product catalog, pricing information, inventory levels, order history

Dependency mapping:

Create dependency map showing relationships:

Order Processing Process
├── Technology
│   ├── ERP System (Critical)
│   ├── Payment Gateway (Critical)
│   ├── Email System (Important)
│   └── Phone System (Important)
├── Personnel
│   ├── Minimum 2 staff
│   ├── Skills: Order entry, customer service
│   └── Remote work capable: Yes
├── Facilities
│   ├── Office space (or remote)
│   └── Internet access (Critical)
└── Vendors
    ├── Internet Provider (Critical)
    ├── Stripe Payment Processing (Critical)
    └── Shipping Carriers (Critical)

Single points of failure:

Identify critical dependencies where no backup exists:
- Only one person knows how to do critical task
- Only one vendor provides critical service
- Only one system provides critical function
- Only one facility can perform critical activity

These are your highest risks and should be addressed in your continuity strategies.

### Step 1.6: Complete and Validate BIA (Week 3-4)

Consolidate BIA results:

Create master BIA document containing:
1. Executive summary (1-2 pages)
   - Purpose and scope
   - Methodology
   - Key findings
   - Critical processes and RTO/RPO
   - Recommendations

Critical business functions summary

Tier 1 processes with RTO/RPO

Impact assessment summary

Dependencies summary

Detailed BIA for each process (appendix)

Full impact analysis

Complete dependency mapping

Resource requirements

Dependencies summary

Detailed BIA for each process (appendix)

Validation process:

1. Review with stakeholders:- Present BIA findings to department heads
- Confirm accuracy of impact assessments
- Validate RTO/RPO are realistic
- Identify any missed processes or dependencies

2. Management review:- Present to executive leadership
- Obtain approval of critical processes and recovery priorities
- Secure budget commitment for recovery strategies
- Get sign-off on BIA document

3. Document and communicate:- Finalize BIA document
- Communicate results to organization
- Use BIA to drive next steps (strategy development, planning)

BIA Findings Report Template:

BUSINESS IMPACT ANALYSIS SUMMARY
Example Corp
Date: [Date]

EXECUTIVE SUMMARY
This BIA identifies [X] critical business processes requiring recovery within 
[X] hours, [Y] important processes requiring recovery within [Y] days, and 
priority recovery objectives.

METHODOLOGY
- Interviews with [X] department heads
- [X] processes analyzed
- Financial, operational, reputational, and compliance impacts assessed
- Recovery objectives (RTO/RPO) established

CRITICAL PROCESSES (TIER 1)
1. Order Processing - RTO: 4 hours, RPO: 1 hour
   Impact: $10K/hour revenue loss, customer loss after 8 hours

2. Payment Processing - RTO: 4 hours, RPO: 0 (no data loss acceptable)
   Impact: $8K/hour revenue loss, compliance violations

[Continue for all Tier 1 processes]

FINDINGS AND RECOMMENDATIONS
1. [X] critical processes require immediate recovery capabilities
2. Current backup strategy meets RPO for [X%] of critical processes
3. [Y] single points of failure identified requiring redundancy
4. Estimated annual financial impact of 24-hour outage: $[X]M
5. Recommended investments: [List key recommendations]

NEXT STEPS
1. Develop continuity strategies for Tier 1 processes
2. Implement redundancy for single points of failure
3. Document recovery procedures
4. Conduct BC/DR testing

Common BIA Mistakes to Avoid:

Too detailed too fast:Don't analyze 200 micro-processes. Start with 20-30 major processes.

Analysis paralysis:Don't spend 6 months on BIA. Get "good enough" data, move to planning, refine later.

Ignoring dependencies:Dependencies are as important as the processes themselves.

Unrealistic RTO/RPO:Don't set 15-minute RTO if you can't actually achieve it.

No stakeholder buy-in:If department heads don't agree with BIA, they won't support the plan.

One-and-done:BIA must be updated annually or when significant changes occur.

## Section 2: Risk Assessment for BC/DR (6-8 pages → 7 pages)

### Why Risk Assessment Matters

The BIA tells you what's critical. Risk assessment tells you what threats you face and how likely they are to disrupt those critical processes.

Risk assessment helps you:- Identify realistic disaster scenarios to plan for
- Prioritize risks (focus on biggest threats first)
- Allocate resources effectively
- Choose appropriate mitigation and recovery strategies
- Justify BC/DR investments to management

### Step 2.1: Identify Threats and Hazards (Week 4)

Goal:Create comprehensive list of potential disasters that could disrupt operations.

Threat categories:

1. Natural Disasters:- Fire
- Flood
- Earthquake
- Hurricane / Tropical storm
- Tornado
- Severe winter storm / Ice storm
- Extreme heat
- Wildfire
- Landslide / Mudslide
- Lightning strike

Note:Vary by geography. Focus on threats realistic for your location.

2. Technology Failures:- Server/hardware failure
- Network outage
- Data loss / corruption
- Software failure / bug
- Cybersecurity incident (ransomware, malware, data breach)
- Cloud service outage
- Telecommunications outage
- Power failure
- HVAC failure (data center overheating)

3. Human-Caused Incidents:- Accidental damage (construction accident, vehicle into building)
- Sabotage / Insider threat
- Theft / Vandalism
- Civil unrest / Riots
- Terrorism
- Workplace violence
- Strikes / Labor disputes

4. Vendor/Supply Chain Failures:- Critical vendor bankruptcy / business closure
- Vendor major outage
- Supply chain disruption
- Service provider failure

5. Pandemic / Public Health:- Pandemic (widespread illness)
- Epidemic (local outbreak)
- Mass food poisoning
- Environmental contamination

6. External Infrastructure Failures:- Regional power grid failure
- Internet backbone failure
- Municipal water failure
- Transportation disruption (roads closed, airports shut down)
- Communication system failure

Threat identification process:

1. Brainstorm potential threats:- Gather team (operations, IT, facilities, safety)
- Review threat categories above
- Identify what could happen at your location
- Don't self-censor - list everything plausible

2. Research historical incidents:- Has your organization experienced disasters before?
- Have local businesses experienced disasters?
- What natural disasters have occurred in your region historically?
- Review FEMA disaster declaration history for your area

3. Consider location-specific risks:- Proximity to flood plain, fault lines, hurricane zones
- Urban vs. rural setting
- Building age and construction
- Shared facility risks (if in multi-tenant building)

4. Industry-specific risks:- Healthcare: HIPAA compliance during disaster, patient safety
- Financial: Regulatory requirements for business continuity
- Manufacturing: Equipment failure, supply chain
- E-commerce: Website downtime, order fulfillment

Threat List Template:

| Threat ID | Threat Name | Category | Description | Geographic Relevance |
| --- | --- | --- | --- | --- |
| NAT-001 | Fire | Natural | Building fire | High - older building |
| NAT-002 | Flood | Natural | River flooding | Medium - near river |
| TECH-001 | Ransomware | Technology | Cyberattack encrypting data | High - all organizations |
| TECH-002 | Server Failure | Technology | Primary server hardware failure | High |
| VEN-001 | ISP Outage | Vendor | Internet service provider major outage | Medium |

### Step 2.2: Assess Likelihood and Impact (Week 4-5)

Goal:Evaluate how likely each threat is and what impact it would have.

Likelihood assessment:

Rate how likely each threat is to occur:

Likelihood Scale:-Very High (5):Almost certain to occur. Has occurred multiple times in past 5 years or occurs annually.
-High (4):Likely to occur. Has occurred once in past 5 years or occurs every few years.
-Medium (3):Possible to occur. Has occurred in region/industry but not specifically to us recently.
-Low (2):Unlikely but possible. Has not occurred to us but theoretically could happen.
-Very Low (1):Very unlikely. Theoretically possible but extremely rare.

Factors affecting likelihood:- Historical data (has it happened before?)
- Geographic location (earthquake in California more likely than in Florida)
- Building age and condition
- Security measures in place
- Technology redundancy
- Industry trends (ransomware likelihood increasing)

Impact assessment:

Rate the potential impact if the threat occurs:

Impact Scale:-Critical (5):Catastrophic impact. Business survival at risk. Revenue loss >$1M or >1 week downtime.
-High (4):Severe impact. Major disruption to critical operations. Revenue loss $100K-$1M or 2-7 day downtime.
-Medium (3):Moderate impact. Significant disruption but workarounds exist. Revenue loss $10K-$100K or 4-48 hour downtime.
-Low (2):Minor impact. Brief disruption, quickly resolved. Revenue loss <$10K or <4 hour downtime.
-Negligible (1):Minimal impact. Little to no disruption.

Consider:- Financial impact (use BIA data)
- Operational impact
- Reputational impact
- Compliance/legal impact
- Safety impact (injuries, loss of life)

### Step 2.3: Analyze and Prioritize Risks (Week 5)

Risk matrix:

Plot likelihood vs. impact to prioritize risks:

IMPACT →
         Low (2)  Medium (3)  High (4)  Critical (5)
      ┌─────────┬──────────┬─────────┬──────────┐
Very  │         │          │         │          │
High  │  Medium │   High   │  High   │ Critical │
(5)   │         │          │         │          │
      ├─────────┼──────────┼─────────┼──────────┤
High  │         │          │         │          │
(4)   │  Medium │  Medium  │  High   │   High   │
      │         │          │         │          │
      ├─────────┼──────────┼─────────┼──────────┤
Med   │         │          │         │          │
(3)   │   Low   │  Medium  │ Medium  │   High   │
      │         │          │         │          │
      ├─────────┼──────────┼─────────┼──────────┤
Low   │         │          │         │          │
(2)   │   Low   │   Low    │ Medium  │  Medium  │
      │         │          │         │          │
      ├─────────┼──────────┼─────────┼──────────┤
Very  │         │          │         │          │
Low   │   Low   │   Low    │  Low    │  Medium  │
(1)   │         │          │         │          │
      └─────────┴──────────┴─────────┴──────────┘

Risk priority:-Critical Risk:Immediate action required. Unacceptable risk level.
-High Risk:Priority focus. Address in near term.
-Medium Risk:Monitor and address as resources allow.
-Low Risk:Accept or minimal mitigation.

Example risk analysis:

| Threat | Likelihood | Impact | Risk Level | Priority | Notes |
| --- | --- | --- | --- | --- | --- |
| Ransomware | High (4) | Critical (5) | CRITICAL | 1 | Industry trend, major impact |
| Building Fire | Low (2) | High (4) | Medium | 5 | Fire suppression system in place |
| ISP Outage | Medium (3) | High (4) | HIGH | 2 | No backup ISP currently |
| Server Failure | Medium (3) | Critical (5) | HIGH | 3 | Aging hardware, no redundancy |
| Flood | Low (2) | Medium (3) | Low | 10 | Not in flood zone |

Focus BC/DR planning on Critical and High risks first.

### Step 2.4: Develop Risk Treatment Strategies (Week 5-6)

Goal:Decide how to address each identified risk.

Risk treatment options:

1. Mitigate (Reduce likelihood or impact):- Implement controls to prevent disaster
- Examples:
  - Fire: Fire suppression system, no smoking policy, electrical inspections
  - Ransomware: Endpoint protection, user training, email filtering, backups
  - Server failure: Redundant servers, proactive maintenance, monitoring

2. Transfer (Insurance or outsourcing):- Shift risk to third party
- Examples:
  - Business interruption insurance
  - Cyber insurance (ransomware coverage)
  - Cloud hosting (provider assumes infrastructure risk)
  - Alternate site agreements

3. Avoid (Eliminate the risk):- Stop activity that creates risk
- Examples:
  - Move data center out of flood zone
  - Exit high-risk business line
  - Discontinue use of vulnerable legacy system

4. Accept (Do nothing, accept consequences):- Knowingly accept risk
- Appropriate for low risks where mitigation cost exceeds potential impact
- Must be conscious decision with management awareness

Risk treatment plan:

For each significant risk, document treatment strategy:

| Threat | Risk Level | Treatment Strategy | Specific Actions | Owner | Timeline | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Ransomware | Critical | Mitigate + Transfer | 1. Implement EDR solution2. User security training3. Offsite backups4. Purchase cyber insurance | IT Mgr | Q1 2025 | $15K |
| ISP Outage | High | Mitigate | 1. Contract backup ISP2. Automatic failover3. Cellular backup | IT Mgr | Q2 2025 | $5K |
| Server Failure | High | Mitigate + Transfer | 1. Migrate to cloud2. Eliminate single server dependency | IT Mgr | Q2 2025 | $20K |
| Building Fire | Medium | Mitigate + Transfer | 1. Fire suppression maintained2. Annual inspection3. Business insurance | Facilities | Ongoing | $2K/yr |

Integration with continuity strategies:

Risk treatment informs your BC/DR strategies:
- Risks you can't completely mitigate require recovery strategies
- High-impact risks justify higher investment in recovery capabilities
- Accepted risks still need recovery plans (even low likelihood events can occur)

## Section 3: Developing Continuity Strategies (8-10 pages → 9 pages)

### Strategy Framework

Continuity strategies answer the question: "HOW will we recover each critical function within its RTO/RPO?"

Strategy categories:

People strategies:How to continue operations when staff unavailable

Technology strategies:How to restore IT systems and data

Facility strategies:How to continue operations when building unavailable

Vendor strategies:How to handle vendor failures

For each critical business function identified in your BIA, develop strategies across these categories.

### Step 3.1: People Strategies (Week 6)

Challenges addressed:- Key employees unavailable (illness, accident, departure)
- Multiple staff unavailable (pandemic, weather emergency)
- Cannot physically come to office (building unavailable, pandemic, weather)

People strategy options:

1. Cross-training and backup assignments:- Cross-train staff so multiple people can perform critical tasks
- Identify backup person for each key role
- Document procedures so backup can step in
- Minimum: Every critical role should have backup

Implementation:- Identify key roles and primary person
- Assign backup person for each
- Create training plan for backups
- Document procedures
- Test backup assignments (have backup perform role for a day)

Example:| Key Role | Primary | Backup | Training Status | Last Tested |
|----------|---------|--------|-----------------|-------------|
| Payroll Processing | Jane Smith | Bob Jones | Complete | Q4 2024 |
| Server Administration | IT Manager | Contractor X | In progress | Not yet |

2. Work from home (remote work):- Enable employees to work remotely
- Critical for building unavailability or pandemic scenarios
- Requires: Laptops, VPN, remote access to systems, communication tools

Implementation:- Identify which positions can work remotely (most office positions)
- Ensure all eligible employees have laptops (not just desktop computers)
- Implement VPN for remote access
- Cloud-based systems (email, collaboration, applications)
- Communication platform (Teams, Slack, Zoom)
- Test WFH capability quarterly

Roles that CAN work remotely:- Office staff, knowledge workers, customer service, sales, management, IT (mostly)

Roles that CANNOT work remotely:- Manufacturing, warehouse, roles requiring physical presence, hands-on customer service

3. Alternate staffing:- Temporary staff, contractors, partners
- Use when own staff insufficient
- Requires pre-arranged agreements or agencies

Implementation:- Identify potential temp agencies or contractors
- Pre-qualify contractors for critical roles (IT support, accounting, etc.)
- Keep contact information current
- Consider retainer agreements for immediate availability

4. Reduced operations:- Operate with reduced staff in emergency mode
- Prioritize critical activities, defer non-critical
- Accept reduced capacity temporarily

Example scenarios:- Pandemic with 30% staff sick: Operate with remaining staff, focus on critical functions only
- Key person unavailable: Backup performs role, may need overtime or outside help

5. Knowledge management:- Document critical procedures and knowledge
- Don't keep critical information in one person's head
- Centralized documentation repository

Implementation:- Standard operating procedures (SOPs) for critical processes
- Runbooks for IT systems
- Contact lists and escalation procedures
- Password management (secure shared vault, not just known by one person)
- Regular documentation review and updates

### Step 3.2: Technology Strategies (Week 6-7)

Goal:Ensure IT systems can be recovered within RTO/RPO.

Technology strategy options:

1. Cloud-based systems (Highest resilience):- Move systems to cloud (SaaS, IaaS, PaaS)
- Provider manages infrastructure redundancy and recovery
- Accessible from anywhere
- Generally: Fastest recovery, lowest internal management burden

Advantages:- Provider responsibility for infrastructure resilience
- Geographic redundancy built-in
- Accessible during facility disaster
- Scalable and flexible

Disadvantages:- Ongoing subscription costs
- Less control over infrastructure
- Internet dependency
- Vendor lock-in potential

Implementation:- Migrate critical systems to cloud (email, file storage, applications)
- Use reputable providers with strong SLAs (Microsoft 365, AWS, Google Cloud, Salesforce)
- Understand provider's DR capabilities
- Still backup your cloud data (provider backups may be limited)

2. Redundant systems (High availability):- Duplicate critical systems with automatic failover
- Primary system fails → Backup system takes over automatically or quickly
- Appropriate for highest criticality systems with very low RTO

Options:-Active-Active:Both systems running, load balanced. Instant failover.
-Active-Passive:Primary running, backup on standby. Quick failover.
-Geographic redundancy:Systems in multiple locations/data centers

Implementation:- Significant investment (2x infrastructure)
- Complex setup and maintenance
- Appropriate for Tier 1 systems with RTO <1 hour
- Cloud providers offer managed redundancy options

3. Backup and restore (Standard approach):- Regular backups of data and systems
- Restore from backup after disaster
- Appropriate for most systems where hours-to-days RTO acceptable

Backup best practices:-3-2-1 rule:3 copies of data, 2 different media types, 1 offsite
-Frequency:Daily minimum for critical data, more frequent for lowest RPO
-Retention:30 days daily backups, weekly/monthly backups retained longer
-Offsite:Backups physically separate from primary location (cloud backup ideal)
-Testing:Quarterly backup restoration tests (verify backups actually work!)
-Encryption:Encrypt backups for security
-Automation:Automated backups, not manual (manual = forgotten)

Backup tools:- Cloud backup services: Backblaze, Carbonite, Veeam Cloud, AWS Backup
- Enterprise backup: Veeam, Commvault, Rubrik, Cohesity
- Database backup: Built-in database tools, AWS RDS backups
- SaaS backup: Spanning, Backupify (backup Microsoft 365, Google Workspace, Salesforce)

4. Alternate data center or co-location:- Secondary data center for failover
- Appropriate for on-premises infrastructure requiring high availability

Options:-Hot site:Fully equipped, running, ready for immediate failover. Most expensive.
-Warm site:Infrastructure ready, data/applications must be restored. Moderate cost.
-Cold site:Empty facility, must bring in everything. Least expensive, longest recovery.

Implementation:- Evaluate: Build secondary data center, co-locate with provider, or use DR-as-a-Service
- Replicate data to alternate site
- Test failover quarterly
- Most organizations moving to cloud instead (more cost-effective)

5. Virtualization and containerization:- Virtual machines and containers easier to backup, migrate, and recover
- Hardware failure doesn't mean complete rebuild
- Can restore VM on different hardware

Implementation:- Virtualize servers where possible (VMware, Hyper-V, KVM)
- Container orchestration (Kubernetes) for cloud-native apps
- Snapshot backups of VMs
- Stored VM images can be restored quickly

6. System imaging and gold builds:- Standard "gold" system images for quick rebuild
- Rather than rebuilding from scratch, restore from image
- Reduces recovery time

Implementation:- Create standard system images for common configurations
- Update images regularly (patches, software versions)
- Store images securely, offsite
- Document restore procedures

7. Service-level agreements (SLAs) with vendors:- Contractual guarantees for system availability and recovery
- Critical for cloud services and managed services
- Ensure SLA meets your RTO/RPO requirements

Implementation:- Review SLAs for all critical services
- Negotiate better SLAs if needed
- Understand what's covered and what's not
- Monitor vendor performance against SLA
- Have recourse if SLA violated (credits, termination)

Technology Strategy Selection Matrix:

| RTO | RPO | Criticality | Recommended Strategy | Cost |
| --- | --- | --- | --- | --- |
| <1 hour | <15 min | Tier 1 | Cloud with redundancy or Active-Active | $$$$ |
| 2-4 hours | 1 hour | Tier 1 | Cloud SaaS or Daily backup with hot standby | $$$ |
| 8-24 hours | 4-8 hours | Tier 2 | Cloud or Daily backup with restore capability | $$ |
| 1-3 days | 24 hours | Tier 2 | Daily backup and restore | $ |
| >3 days | >24 hours | Tier 3 | Weekly backup | $ |

SMB practical technology strategy:

For small businesses, recommended approach:
-Cloud-first:Migrate as much as possible to cloud (email, files, applications)
-Daily backups:All remaining on-premises data backed up daily to cloud
-Test quarterly:Restore from backup every quarter
-Document:Recovery procedures for each system
-Budget:$500-5,000/month depending on size

Enterprise technology strategy:

For large organizations, recommended approach:
-Hybrid cloud:Mix of cloud and on-premises, integrated
-Redundancy for Tier 1:Active-active or active-passive for most critical systems
-Robust backup:Enterprise backup solution with multiple retention tiers
-Alternate site:Warm or hot site for critical infrastructure
-Automation:Automated failover and recovery processes
-Budget:$50,000-$500,000+ annually depending on scale

### Step 3.3: Facility Strategies (Week 7)

Goal:Enable operations to continue when primary facility unavailable.

Facility strategies:

1. Work from home (Most cost-effective):- Employees work remotely during facility disruption
- Appropriate for: Office workers, knowledge workers, customer service
- Not appropriate for: Manufacturing, warehouse, physical customer service

Requirements:- Remote access capability (VPN, cloud systems)
- Laptops (not just desktops)
- Home internet (assume most employees have this)
- Communication tools (email, video conferencing, phone)

Implementation:- Ensure all office employees have laptops or ability to work remotely
- Test WFH capability before disaster
- Communication plan for WFH coordination
- Policies for WFH during disaster (expectations, hours, etc.)

2. Alternate work site:- Temporary office space when primary unavailable
- Appropriate for: Roles requiring office, meeting customers, specialized equipment

Options:

a. Executive suites/serviced offices:- Fully furnished offices available on short-term contracts
- Pros: Available quickly, fully equipped (furniture, internet, phones)
- Cons: Cost ($2,000-10,000+/month), limited availability during regional disaster
- Providers: Regus, WeWork, local executive suites

b. Co-working spaces:- Shared office spaces, desks by the day/month
- Pros: Flexible, cost-effective, available in most cities
- Cons: Limited privacy, may not accommodate full team
- Providers: WeWork, local co-working spaces

c. Partner company space:- Arrangement with friendly non-competitor to use their space temporarily
- Pros: Potentially low cost or reciprocal, builds relationships
- Cons: May not be available when needed, depends on relationship

d. Alternate company location:- If multi-location company, use other location
- Pros: Company-controlled, familiar environment
- Cons: Not all companies have multiple locations, may be far from employees

e. Hotel conference rooms:- Short-term solution for meeting space
- Pros: Available quickly, no long-term commitment
- Cons: Expensive, no permanent workspace, no specialized equipment

Implementation:- Research options in advance (don't wait for disaster)
- Pre-identify providers and get contact information
- If possible, pre-negotiate agreements (faster activation)
- Document activation procedures
- Budget for alternate site (company pays temporarily, insurance may reimburse)

3. Mobile/temporary facilities:- Temporary buildings, trailers, mobile offices
- Appropriate for: Warehouse, manufacturing, specialized operations

Implementation:- Identify providers of mobile facilities
- Assess site requirements (where could temporary facility be placed?)
- Plan for utilities (power, water, internet)
- Permitting considerations (may delay deployment)
- Best for: Longer-term recovery (not immediate solution)

4. Third-party recovery site services:- Specialized disaster recovery providers offer pre-contracted space

Options:-Hot site:Fully equipped, ready immediately. Most expensive ($10,000-50,000+/month standby fee plus usage).
-Warm site:Basic infrastructure, bring in equipment. Moderate cost.
-Cold site:Empty space, set up from scratch. Least expensive.
-Mobile recovery sites:Providers bring mobile facilities to your site.

Providers:Sungard, IBM, Agility Recovery, other DR service providers

When to consider:- Large enterprise with complex recovery requirements
- Regulatory requirements for alternate site
- Mission-critical operations with very low RTO
- Budget for comprehensive DR capability

Implementation:- RFP process for DR site providers
- Contract for appropriate level (hot/warm/cold)
- Test site annually (actual activation and operation)
- Keep documentation and contact info current

Facility Strategy Decision Matrix:

| Scenario | Outage Duration | Business Size | Recommended Strategy | Cost |
| --- | --- | --- | --- | --- |
| Office damaged | Days-weeks | SMB | Work from home | $ |
| Office destroyed | Months | SMB | WFH + Executive suite for essential roles | $$ |
| Office damaged | Days-weeks | Enterprise | WFH + Activate warm site | $$$ |
| Office destroyed | Months | Enterprise | WFH + Hot site or long-term office rental | $$$$ |
| Manufacturing | Any | Any size | Mobile facility or partner production | $$$$ |

### Step 3.4: Vendor Strategies (Week 7-8)

Goal:Ensure vendor failures don't stop critical operations.

Vendor strategies:

1. Diversification (Backup vendors):- Multiple vendors for critical services
- If primary vendor fails, switch to backup
- Appropriate for: Critical suppliers, internet/telecom, key service providers

Implementation:- Identify critical vendors (single points of failure)
- Qualify backup vendors
- Maintain relationships with backups (small orders periodically)
- Keep backup vendor contact information current
- Document switchover procedures

Example:- Primary ISP: Comcast Business
- Backup ISP: AT&T Business
- Automatic failover or manual switchover within 4 hours

2. Vendor contingency requirements:- Require vendors to have their own BC/DR plans
- Contractual requirements for vendor availability
- Right to audit vendor BC/DR capabilities

Implementation:- Include BC/DR requirements in vendor contracts
- Request vendor BC/DR plan and test results
- Critical vendors: Right to audit their DR capabilities
- Understand vendor's RTO/RPO
- Ensure vendor RTO meets your needs

3. Service level agreements (SLAs):- Contractual guarantees for vendor availability and performance
- Financial penalties if vendor fails to meet SLA

Implementation:- Negotiate SLAs with critical vendors
- Ensure SLA matches your RTO/RPO requirements
- Monitor vendor performance against SLA
- Hold vendors accountable (request credits for SLA violations)
- Consider termination rights if repeated violations

4. Inventory and stockpiling:- Maintain buffer inventory of critical supplies
- Provides cushion if supplier disrupted

Implementation:- Calculate typical usage and lead times
- Maintain [X] days/weeks of inventory
- Balance cost of holding inventory vs. risk of stockout
- Monitor inventory levels and reorder points

5. Vendor monitoring and early warning:- Monitor vendor health and stability
- Early warning allows proactive action

Implementation:- Monitor vendor financial stability (credit reports, news)
- Relationships with vendor account managers (warn of issues)
- Industry news and trends
- Diversify before vendor fails (not after!)

Critical Vendor Assessment Template:

| Vendor | Service Provided | Criticality | Backup Vendor | SLA | Last Tested | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| ISP A | Internet | Critical | ISP B | 99.9% | Q4 2024 | Automatic failover configured |
| Supplier X | Raw materials | Important | Supplier Y | Standard terms | Q3 2024 | 2-week inventory buffer |
| Cloud Provider | Application hosting | Critical | N/A | 99.95% | Ongoing | Provider multi-region redundancy |

## Section 4: Creating Recovery Procedures (10-12 pages → 11 pages)

### Why Procedures Matter

During a disaster, people are stressed and may not think clearly. Detailed, step-by-step procedures ensure recovery happens consistently and completely.

Good procedures are:-Step-by-step:Specific actions in order
-Clear:Written for person who may not be expert
-Complete:All steps included, nothing assumed
-Tested:Validated through exercises and real incidents
-Accessible:Available when needed (not just on office server that's down!)

### Step 4.1: Document IT Disaster Recovery Procedures (Week 8-10)

Goal:Step-by-step procedures to recover each critical IT system within RTO.

DR procedure components:

1. System overview:- System name and description
- Business functions supported
- Criticality tier and RTO/RPO
- Owner and support contacts

2. Normal operating state:- How system normally operates
- Key indicators system is healthy
- Baseline performance metrics

3. Disaster indicators:- How to know system has failed or is in disaster state
- Monitoring alerts
- User reports
- System unavailable

4. Initial response:- Immediate actions (assess, notify, isolate if necessary)
- Who to contact
- Disaster declaration criteria

5. Recovery procedure:- Step-by-step recovery instructions
- Detailed enough for someone to follow who isn't primary admin
- Alternative steps if preferred method doesn't work
- Verification steps (how to confirm recovery successful)

6. Return to normal:- Cutover from disaster mode to normal operations
- Transition procedures
- Monitoring for stability

7. Post-recovery:- Lessons learned
- Documentation updates
- Reporting

DR Procedure Template:

SYSTEM RECOVERY PROCEDURE
System: [System Name]
RTO: [X hours]  |  RPO: [X hours]
Owner: [Name]  |  Support: [Contact]

──────────────────────────────────────────────────
1. DISASTER DETECTION

The [system name] disaster recovery procedure is invoked when:
- System unavailable for >15 minutes
- Monitoring alerts: [specific alerts]
- Users report system down
- Data corruption detected
- Hardware failure confirmed

──────────────────────────────────────────────────
2. INITIAL RESPONSE (First 15 minutes)

Step 1: Assess situation
- Determine nature of failure: [Hardware? Software? Network? Data?]
- Estimate impact: [Is it total system failure or partial?]
- Estimate recovery time: [Can fix quickly or need DR procedure?]

Step 2: Notify stakeholders
- Notify: IT Manager, System Owner, Business Continuity Manager
- Use: Phone call (do not rely on email if systems down)
- Contacts: [Phone numbers]

Step 3: Declare disaster (if appropriate)
- If recovery will take > [X hours], declare disaster
- IT Manager or Owner declares
- Activates full DR procedure

──────────────────────────────────────────────────
3. RECOVERY PROCEDURE

[Detailed step-by-step procedure for this specific system]

Step 1: Prepare recovery environment
- [ ] Access backup server at [location/IP]
- [ ] Verify backup server operational
- [ ] Ensure sufficient storage space: [X GB required]
- [ ] Network connectivity confirmed

Step 2: Retrieve backup
- [ ] Access backup system: [URL/path]
- [ ] Authenticate: Username [username], Password [location of password]
- [ ] Identify most recent good backup: [how to identify]
- [ ] Verify backup date/time acceptable per RPO
- [ ] Initiate backup download/restore

Step 3: Restore data
- [ ] Run restore command: [specific command/procedure]
- [ ] Monitor progress: [expected time: X hours]
- [ ] Verify restore completed without errors
- [ ] Check restore logs: [log location]

Step 4: Verify data integrity
- [ ] Run data validation checks: [specific checks]
- [ ] Compare record counts to expected
- [ ] Test sample records
- [ ] Verify data completeness

Step 5: Configure system
- [ ] Apply system configuration: [config file location]
- [ ] Verify all required services running
- [ ] Test connectivity from client machines
- [ ] Update DNS if IP changed

Step 6: Test functionality
- [ ] Run standard health checks
- [ ] Test critical functions: [list specific tests]
- [ ] Have business user perform test transaction
- [ ] Verify expected behavior

Step 7: Resume operations
- [ ] Notify users system available
- [ ] Provide access instructions if different
- [ ] Monitor closely for issues
- [ ] Status: Recovery complete at [time]

──────────────────────────────────────────────────
4. VERIFICATION AND MONITORING

Post-recovery monitoring (first 24 hours):
- [ ] Monitor system performance
- [ ] Watch for errors or unexpected behavior
- [ ] User feedback - any issues?
- [ ] Verify backups resumed normally

Success criteria:
- System operational within RTO: [X hours]
- Data loss within RPO: [X hours]
- All critical functions operational
- Users can perform normal work

──────────────────────────────────────────────────
5. TROUBLESHOOTING

Common issues and solutions:

Issue: Backup file corrupted or missing
Solution: Try previous day's backup, may lose more data but better than nothing

Issue: Insufficient disk space for restore
Solution: Delete temporary files, expand storage, or use alternate server

Issue: Restore takes longer than expected
Solution: Monitor progress, if too slow consider partial restore of critical data only

If recovery not proceeding successfully:
- Escalate to: [Vendor support / Senior IT staff]
- Escalation contacts: [Phone numbers]
- Consider alternate recovery strategies: [list alternatives]

──────────────────────────────────────────────────
6. DOCUMENTATION

After recovery complete, document:
- What happened (root cause)
- Timeline of events
- Steps taken
- Actual recovery time
- Data loss amount
- Issues encountered
- Lessons learned
- Recommendations for improvement

Submit report to: Business Continuity Manager
Within: 48 hours of recovery

Create DR procedures for each critical system identified in BIA.

Tips for writing DR procedures:

Write for your backup person, not yourself: Assume the person following this might not be the expert. Explain what to do, not just what commands to run.

Include decision trees: "If X, do Y. If not X, do Z." Real disasters don't follow script perfectly.

Specific, not generic: "Run restore command: restore-database.sh --backup=/backups/latest --target=/mnt/data" not "Restore the database."

Include credentials and access info: Where are passwords stored? How to access systems? (Securely document, not plain text in procedure!)

Screenshots help: Especially for GUI-based procedures.

Test the procedure: Have someone else follow your procedure. If they get stuck, procedure needs clarification.

Version control: Update procedures when systems change. Date each procedure, maintain version history.

Accessible format: Not just on the server that might be down. Print copy, USB drive, cloud storage.

Write for your backup person, not yourself:Assume the person following this might not be the expert. Explain what to do, not just what commands to run.

Include decision trees:"If X, do Y. If not X, do Z." Real disasters don't follow script perfectly.

Specific, not generic:"Run restore command:restore-database.sh --backup=/backups/latest --target=/mnt/data" not "Restore the database."

Include credentials and access info:Where are passwords stored? How to access systems? (Securely document, not plain text in procedure!)

Screenshots help:Especially for GUI-based procedures.

Test the procedure:Have someone else follow your procedure. If they get stuck, procedure needs clarification.

Version control:Update procedures when systems change. Date each procedure, maintain version history.

Accessible format:Not just on the server that might be down. Print copy, USB drive, cloud storage.

### Step 4.2: Document Business Continuity Procedures (Week 10-11)

Goal:Step-by-step procedures to continue critical business functions in alternate mode.

BC procedures answer:"How do we keep doing this critical function if our normal systems/facility/staff are unavailable?"

BC Procedure Template:

BUSINESS FUNCTION CONTINUITY PROCEDURE
Function: [Function Name]
Department: [Department]
RTO: [X hours]

──────────────────────────────────────────────────
1. FUNCTION OVERVIEW

What this function does:
[Brief description of the business function]

Why it's critical:
[Impact if this function stops - revenue, compliance, customers]

Normal operations:
- Staff required: [X people with Y roles]
- Location: [Primary office location]
- Systems: [Systems normally used]
- Peak times: [When this function busiest]

──────────────────────────────────────────────────
2. ALTERNATE OPERATING MODES

This function can be performed in these alternate modes:

Mode A: Work from Home
- Staff work remotely
- Use cloud-based systems
- RTO: [X hours]
- Suitable for: Building unavailable, pandemic

Mode B: Alternate Office Location
- Relocate to [executive suite / partner location / other office]
- Use temporary equipment
- RTO: [X hours]
- Suitable for: Extended building unavailability

Mode C: Manual/Degraded Operations
- Manual workarounds if systems unavailable
- Reduced capacity
- RTO: [X hours] for emergency mode
- Suitable for: IT systems down, recovery in progress

──────────────────────────────────────────────────
3. MODE A: WORK FROM HOME PROCEDURE

Activation triggers:
- Building unavailable
- Pandemic / Stay-at-home order
- Weather emergency preventing travel

Step 1: Notify staff (Operations Manager)
- [ ] Send email/text to all department staff
- [ ] Message: "Activating WFH for [function]. Begin working from home immediately."
- [ ] Provide WFH expectations and instructions

Step 2: Ensure remote access (IT Manager)
- [ ] Verify all staff have VPN access
- [ ] Verify all staff have laptops
- [ ] Provide IT support for connection issues
- [ ] Hotline for tech issues: [Phone]

Step 3: Resume operations remotely (Department Manager)
- [ ] Staff log in from home
- [ ] Daily check-in video calls: [Time]
- [ ] Use [Teams/Slack] for communication
- [ ] Prioritize critical activities
- [ ] Track work completion

Step 4: Monitor and support
- [ ] Manager monitors productivity and issues
- [ ] Address technology or access problems quickly
- [ ] Adjust as needed based on duration

Equipment needs for WFH:
- Laptop (company-provided)
- Home internet (assume staff have)
- VPN access
- Phone (cell phone or VoIP softphone)
- Access to cloud systems: [list systems]

Expected capacity:
- 80-100% of normal capacity (slight reduction due to WFH challenges)

Duration capability:
- Indefinite (can work from home as long as needed)

──────────────────────────────────────────────────
4. MODE B: ALTERNATE OFFICE PROCEDURE

Activation triggers:
- Building unavailable for > 3 days
- Cannot work from home (equipment, security, collaboration needs)

Step 1: Secure alternate location (Operations Manager)
- [ ] Contact pre-identified executive suite: [Company, Phone]
- [ ] Reserve space for [X] staff
- [ ] Confirm availability and pricing
- [ ] Arrange access (keys, badge access)
- [ ] Expected cost: $[X]/month

Step 2: Set up alternate location (IT + Facilities)
- [ ] Install internet connection (or verify existing)
- [ ] Set up workstations (bring laptops or desktops)
- [ ] Configure phones (forward main number)
- [ ] Test all systems and connectivity
- [ ] Set up printers/peripherals if needed

Step 3: Relocate staff (Department Manager)
- [ ] Notify staff of alternate location address
- [ ] Provide directions and parking information
- [ ] Schedule first day orientation
- [ ] Assign workspaces

Step 4: Resume operations
- [ ] Staff report to alternate location
- [ ] Operate normal business hours
- [ ] Manager monitors operations
- [ ] Communicate with customers about temporary location if needed

Duration capability:
- 1-6 months (while primary office repaired)
- Long-term: May need to find permanent alternate if primary unrecoverable

──────────────────────────────────────────────────
5. MODE C: MANUAL / DEGRADED OPERATIONS

Activation triggers:
- IT systems down but staff available
- Temporary workaround while systems recovered

Limitations:
- Reduced capacity (50-70% of normal)
- Manual processes slower and more error-prone
- Not sustainable long-term (hours to days only)

Manual procedures for this function:

[Detailed manual workaround procedures - example for Order Processing:]

Step 1: Accept orders manually
- [ ] Answer phones manually (if phone system down, use cell phones)
- [ ] Record orders on paper forms: [Form location]
- [ ] Capture: Customer name, contact, items, quantities, delivery address, payment

Step 2: Process orders manually
- [ ] Check inventory manually: [Where inventory records stored?]
- [ ] Calculate pricing: [Price list location]
- [ ] Create manual invoice: [Invoice form location]

Step 3: Fulfill orders
- [ ] Write picking ticket by hand
- [ ] Give to warehouse for fulfillment
- [ ] Manual shipping process

Step 4: Record for later entry
- [ ] Keep all paper records organized
- [ ] When systems restored, enter all manual orders into system
- [ ] Verify no orders lost

Risks of manual mode:
- Errors (incorrect orders, wrong prices, lost papers)
- Slow (much slower than systems)
- Limited capacity
- Data entry required later (double work)

Use manual mode only as temporary bridge until systems recovered!

──────────────────────────────────────────────────
6. COMMUNICATION

Notify these stakeholders when activating continuity:
- Department staff: [Method]
- Customers: [If customer-facing function affected]
- Vendors: [If affects vendor interactions]
- Management: Status reports daily

Communication templates: [Link to templates]

──────────────────────────────────────────────────
7. RETURN TO NORMAL

When primary facility/systems available:
- [ ] Notify staff of return date
- [ ] Coordinate move back
- [ ] Verify all systems operational
- [ ] Resume normal operations
- [ ] Catch up any backlog from disaster
- [ ] Conduct lessons learned review

──────────────────────────────────────────────────
8. RESOURCES

Contacts:
- Department Manager: [Name, Phone]
- Operations Manager: [Name, Phone]
- IT Support: [Phone]

Supplies:
- Manual forms: [Location]
- Equipment: [List]

Documents:
- Standard operating procedures: [Link]
- Price lists: [Link]
- Customer list: [Link]

Create BC procedures for each critical business function identified in BIA.

### Step 4.3: Test Your Procedures (Week 12)

Goal:Validate procedures actually work before you need them in real disaster.

Testing approach:

1. Desktop review:- Read through procedures
- Check for completeness, accuracy, clarity
- Update any outdated information
- Quick validation: 1-2 hours per procedure

2. Walkthrough exercise:- Gather team and walk through procedure step-by-step verbally
- "If this happened, we'd do step 1... then step 2..."
- Identify gaps, unclear steps, missing information
- Update procedure based on findings
- Time: 2-3 hours per procedure

3. Hands-on test:- Actually execute the procedure
- For IT DR: Restore from backup in test environment
- For BC: Have staff work from home for a day, or actually set up at alternate location
- For manual mode: Process orders manually for an hour
- Comprehensive validation but more disruptive
- Time: Half-day to full-day per procedure

Testing schedule:- Year 1: Desktop review all procedures, walkthrough critical procedures
- Ongoing: Annual hands-on test of critical procedures, walkthrough of others

After testing:- Document results (what worked, what didn't)
- Update procedures based on findings
- Report results to management
- Schedule next test

## Section 5: Crisis Communication Planning (5-6 pages → 5.5 pages)

### Why Communication Matters

During disaster, communication is as critical as technical recovery. Stakeholders need to know:
- What happened
- Is everyone safe
- What's the impact
- What you're doing about it
- When things will be back to normal

Poor communication causes:- Panic and confusion
- Rumor and misinformation
- Loss of confidence (customers, employees, investors)
- Additional questions and calls (overwhelming your team)

Good communication provides:- Clarity and confidence
- Reduced anxiety
- Maintained relationships
- Controlled narrative

### Step 5.1: Identify Communication Stakeholders (Week 11)

Internal stakeholders:- Employees (all staff need to know)
- Management and executives
- Board of directors (for significant disasters)

External stakeholders:- Customers (especially if service affected)
- Vendors and suppliers
- Partners and resellers
- Investors and shareholders (if applicable)
- Media and public (for major disasters)
- Regulators (if applicable - report certain incidents)

For each stakeholder group, identify:- What they need to know
- How much detail to provide
- How to communicate with them
- Who communicates with them

### Step 5.2: Develop Communication Templates (Week 11-12)

Create templates for common communication scenarios:

Template 1: Initial Employee Notification

Subject: URGENT: [Brief description of incident]

Team,

This message is to inform you of [brief description of situation/incident].

SAFETY: [Status of personnel safety - "All personnel safe and accounted for" 
or "We are in process of accounting for all personnel"]

SITUATION: [1-2 sentence description of what happened and current situation]

IMMEDIATE ACTIONS:
- [Action 1: e.g., "Office is closed today"]
- [Action 2: e.g., "Work from home if possible"]
- [Action 3: e.g., "Do not attempt to enter building"]

NEXT STEPS: [What we're doing to respond and recover]

NEXT UPDATE: [When they'll hear from us again - "By 5pm today" or "Tomorrow morning"]

QUESTIONS: [Who to contact with questions and how]

STAY SAFE: Your safety is our top priority.

[Name]
[Title]
[Contact Information]

Template 2: Employee Status Update

Subject: UPDATE: [Incident name] - Day [X]

Team,

Providing update on [incident] recovery.

CURRENT STATUS: [Brief status - "Building still unavailable" or "Systems 
75% recovered" or "Operations resumed at reduced capacity"]

WHAT'S HAPPENED: [Progress since last update]

WHAT'S NEXT: [What we're working on next]

EXPECTATIONS FOR TOMORROW: [What should employees expect/do tomorrow]

TIMELINE: [Estimated timeline for full recovery if known]

QUESTIONS: [Contact for questions]

Thank you for your patience and continued work during this time.

[Name]

Template 3: Customer Notification

Subject: Service Update: [Brief description]

Dear Valued Customer,

We are currently experiencing [brief description of situation] that is 
temporarily affecting [what services/products affected].

WHAT HAPPENED: [Brief explanation - be honest but not overly detailed]

IMPACT TO YOU: [Specifically what customers can expect - delays, service 
unavailability, etc.]

WHAT WE'RE DOING: [Actions we're taking to resolve]

TIMELINE: [Expected resolution time if known, or "We will update you 
within [X hours]"]

FOR URGENT ISSUES: [Alternative contact method or emergency support]

We sincerely apologize for any inconvenience and appreciate your patience 
as we work to restore normal operations.

[Name]
[Title]
[Company]
[Contact Information]

Template 4: Vendor Notification

Subject: Operations Update: [Company Name]

Dear [Vendor Name],

We are currently experiencing [brief description] that may impact 
our normal business operations with you.

POTENTIAL IMPACT:
- [Impact 1: e.g., "Delayed payment processing"]
- [Impact 2: e.g., "Unable to accept deliveries"]
- [Impact 3: e.g., "Order volume may be reduced"]

TIMELINE: [Expected duration]

WHAT WE NEED FROM YOU: [Any specific actions or support needed from vendor]

We will keep you informed as the situation progresses.

[Name]
[Contact Information]

Template 5: All-Clear / Return to Normal

Subject: RESOLVED: [Incident name] - Operations Resumed

Team/Customers,

We are pleased to inform you that we have successfully recovered from 
[incident] and normal operations have resumed.

RESOLUTION: [Brief description of how incident was resolved]

STATUS: [All systems operational / Office reopened / etc.]

RETURN TO NORMAL: [When to return to office / resume normal procedures]

BACKLOG: [If applicable: "We are working through backlog and appreciate 
your patience"]

THANK YOU: [Thank everyone for patience, support, and efforts]

PREVENTION: [Briefly mention steps taken to prevent recurrence, if appropriate]

Questions? [Contact information]

[Name]

### Step 5.3: Establish Communication Protocols (Week 12)

Communication roles:

Spokesperson:- Owner/CEO is primary external spokesperson
- Operations Manager is primary internal spokesperson
- Backup designees identified
- Only designated spokespeople communicate with media

Message coordination:- All external communications reviewed by [Owner/Communications Team] before sending
- Ensures consistent message
- Prevents contradictory information
- Emergency exception: If time-critical, communicate first, coordinate later

Communication channels:

Internal:- Primary: Email (all-staff distribution list)
- Backup: Text message (if email down)
- Alternative: Phone tree (call each person who calls others)
- Emergency: Voicemail to office phone (if calling in)

External (Customers):- Email (customer database)
- Website banner/notification
- Social media (Twitter, LinkedIn, Facebook)
- Phone: Updated outgoing voicemail message
- For inquiries: Dedicated response team or queue

External (Media):- Press release (if warranted)
- Owner/designated spokesperson only
- Coordinate with PR firm if applicable

Communication frequency:

During active disaster:- Internal: At least daily, more frequent if rapidly changing
- Customers: Initial notification + updates every 1-2 days + resolution
- Set expectations for next update in every communication

After recovery:- Final "all clear" message
- Thank you and lessons learned (optional, appropriate for long/significant disasters)

Communication log:

Maintain log of all disaster communications:
- Date/time sent
- Stakeholder group (internal, customer, vendor, media)
- Channel (email, social media, press release)
- Key message summary
- Sent by whom

Log helps: Track communication cadence, avoid redundant messages, support lessons learned

### Step 5.4: Media Relations (If Applicable)

When to engage media:- Significant disaster affecting community (building fire, hazmat incident)
- Public safety implications
- Major customer impact
- Regulatory reporting requires public disclosure
- Media already covering story (may not be a choice)

Media relations guidelines:

1. Designated spokesperson only:- Owner/CEO or designated spokesperson
- Refer all media inquiries to spokesperson
- Do NOT have employees talk to media without authorization

2. Prepare key messages:- What happened (facts only, no speculation)
- What we're doing about it
- Concern for safety and customers
- Confidence in recovery
- When more information will be available

3. Be honest:- Don't speculate or guess
- "We're still investigating" is acceptable answer
- Don't say "no comment" (sounds guilty)
- If you don't know, say so and commit to finding out

4. Control the narrative:- Proactive communication better than reactive
- Issue press release with facts before media requests if possible
- Provide timely updates
- Correct misinformation quickly

5. Monitor media coverage:- Track what's being reported
- Correct factual errors
- Respond to serious misreporting

6. Social media monitoring:- Watch social media for customer complaints and rumors
- Respond professionally and quickly
- Direct to appropriate channel for support

7. Get expert help:- Crisis PR firms for major disasters
- Legal counsel for media inquiries about litigation, regulatory issues
- Don't wing it with major incidents

## Section 6: Testing Program Setup (6-8 pages → 7 pages)

### Why Testing is Non-Negotiable

Untested plans don't work in real disasters.Period.

Testing accomplishes:
-Validates procedures actually work(many look good on paper but fail in execution)
-Identifies gaps and issues(missing steps, outdated info, unclear procedures)
-Builds confidence and reduces stress(team knows what to do)
-Develops muscle memory(team practices their roles)
-Meets compliance requirements(SOC 2, HIPAA, ISO 27001 all require testing)

Reality check:Most organizations have BC/DR plans. Most have never tested them. When disaster strikes, they discover their plan doesn't work. Don't be that organization.

### Step 6.1: Design Your Testing Program

Testing approach:

Annual minimum:At least one test annually of your entire BRRP (compliance requirement)

Recommended:Multiple tests annually using different methods:
- Quarterly: Lightweight tests (tabletop, backup restoration)
- Annually: Comprehensive test (full DR exercise or partial operational exercise)

Testing progression over time:

Year 1:Establish baseline
- Tabletop exercise (walkthrough)
- Backup restoration test
- Work from home test

Year 2:Increase rigor
- Add functional tests (actually recover specific systems)
- Test alternate site if applicable
- Cross-train and test backup personnel

Year 3+:Mature program
- Full DR exercises with actual failover
- Surprise/unannounced tests (higher stress, more realistic)
- Multi-scenario tests (building + IT disaster simultaneously)
- Integration with incident response testing

### Step 6.2: Testing Methods

Method 1: Tabletop Exercise (Easiest, Start Here)

What it is:- Facilitated discussion walking through disaster scenario
- Team sits around table (or video call) and talks through response
- "If X happened, what would we do?" "Who would you call?" "Where is that information?"

Advantages:- Low cost, low disruption
- Quick (2-3 hours)
- Good for finding gaps in plan and lack of awareness
- Non-threatening, low stress

Disadvantages:- Not hands-on (don't actually DO anything)
- Can't validate technical procedures actually work
- Easy to say "we'd do X" without proving you can

How to conduct:

Before the exercise:1. Schedule 2-3 hours with key recovery team
2. Select scenario (building fire, ransomware, key system failure)
3. Prepare scenario details (what happened, when, impacts)
4. Review BRRP so team familiar
5. Prepare discussion questions

During the exercise:1. Present scenario: "At 8am this morning, we discovered..."
2. Walk through timeline: "It's now 9am. What do you do?"
3. Team discusses and describes actions
4. Facilitator asks questions:
   - "Who would you call?"
   - "Where is that contact information?"
   - "What systems do you need to check?"
   - "How long would that take?"
   - "What if that doesn't work?"
5. Note issues: Missing info, unclear procedures, disagreement about process
6. Continue through recovery: Hour by hour or phase by phase

After the exercise:1. Debrief: What went well? What issues discovered?
2. Document findings
3. Action items to address gaps
4. Update BRRP based on findings

Tabletop Exercise Scenarios (Choose One):

Scenario A: Building Fire- Time: 7am Monday morning
- Situation: Fire in building overnight, discovered by security
- Status: Building unsafe to enter, closed indefinitely (weeks to months)
- Impact: All equipment in building inaccessible
- Question: How do you enable staff to work? How do you access data?

Scenario B: Ransomware Attack- Time: 9am Tuesday
- Situation: IT discovers ransomware encrypted critical servers
- Status: Primary systems down, ransom demand received
- Impact: Order system, customer database, email unavailable
- Question: How do you recover data? How long? Do you pay ransom?

Scenario C: Key Person Unavailable- Time: 8am Friday
- Situation: Your IT Manager had serious car accident, hospitalized, out 3+ months
- Status: Only person with admin access to several critical systems
- Impact: No one else can manage servers, backups, network
- Question: How do you access systems? Who takes over responsibilities?

Scenario D: Vendor Failure- Time: Ongoing
- Situation: Critical supplier filed for bankruptcy, ceased operations immediately
- Status: Can't get raw materials / parts / service needed for operations
- Impact: Can't fulfill customer orders within 2 weeks
- Question: How do you find alternative supplier quickly? How do you keep operating?

Method 2: Backup Restoration Test (Critical)

What it is:- Actually restore data from backup to verify it works
- Proves backups are good and restoration process works
- Technical test, not business process test

Advantages:- Validates most critical DR component (backup and restore)
- Catches backup failures before disaster
- Proves RTO/RPO achievable
- Builds IT team confidence and expertise

Disadvantages:- Technical skill required
- Requires test environment (don't restore over production!)
- Time-consuming (hours depending on data size)

Frequency:Quarterly minimum, monthly even better

How to conduct:

Select system to test:Pick critical system from BIA

Identify backup to restore:Most recent daily backup

Prepare test environment:

Separate from production (don't overwrite production data!)

Could be: Spare server, cloud test environment, VM

Perform restoration:

Follow DR procedure for this system

Restore backup to test environment

Time the restoration (validate RTO)

Verify restoration:

Data completely restored?

Correct data and time period? (Validate RPO)

Can application access and use data?

Integrity checks pass?

Functional test:

Have business user test the restored system

Can they perform normal work?

Any data missing or corrupted?

Document results:

Restoration successful? How long did it take?

Any issues encountered?

Backup verified good

Red flags that require immediate attention:- Backup doesn't exist or is corrupted
- Restoration fails or is incomplete
- Data is old (older than RPO)
- Restoration takes much longer than RTO
- Application can't use restored data

If backup test fails:This is a crisis. Your DR capability is broken. Fix immediately before disaster occurs.

Method 3: Work from Home Test

What it is:- Employees actually work from home for a day
- Tests WFH capability and alternate work arrangements
- Validates remote access, VPN, communication tools

Advantages:- Tests critical continuity strategy (WFH)
- Identifies issues with remote access, home internet, equipment
- Low risk (if fails, just come to office tomorrow)
- Builds familiarity and comfort with WFH

Disadvantages:- Somewhat disruptive (not normal work environment)
- Customer-facing impacts (harder to schedule meetings, etc.)
- Doesn't test technical recovery (just alternate work location)

Frequency:Annually minimum

How to conduct:

Select test date:Pick relatively slow day, avoid month-end or major deadlines

Communicate to team:

"Next Thursday is WFH disaster recovery test"

"Everyone work from home as if office unavailable"

"Test remote access and WFH procedures"

Day before test:

Remind everyone

Ensure everyone has laptops and VPN access

IT verifies remote access working

Test day:

All staff work from home

Manager checks in with team (video call)

Normal work performed remotely

Staff reports any issues (can't connect, VPN problems, missing access)

End of day debrief:

Survey: How did it go? Any problems?

IT: Technical issues encountered?

Operations: Could we sustain this long-term?

Document findings:

What worked well

What issues discovered (fix before next test)

Update procedures

Common WFH test findings:- Some employees don't have laptops (only desktop in office)
- VPN slow or connection problems
- Home internet insufficient for video calls
- Access to certain systems not working remotely
- Communication challenges (harder to collaborate)

Address all findings before next test.

Method 4: Functional Recovery Test (Advanced)

What it is:- Actually perform recovery procedure for specific system
- More hands-on than tabletop, less disruptive than full DR test
- Proves technical procedures work

Example:- Test: Failover from primary server to backup server
- Process: Simulate primary server failure, execute failover procedure, verify backup server operational
- Impact: May require maintenance window for production, or do in test environment

Advantages:- Validates procedures actually work
- Team performs actual recovery steps
- Identifies technical issues in procedures
- More realistic than tabletop

Disadvantages:- More complex and time-consuming
- May require downtime or after-hours work
- Risk of impacting production if not careful

Frequency:Annually for critical systems

How to conduct:

Select system and recovery procedure to test

Plan test carefully:

Determine impact to production (if any)

Schedule maintenance window if needed

Prepare rollback plan if test fails

Notify stakeholders

Execute recovery procedure:

Follow DR procedure step-by-step

Note time required for each step

Document any issues or deviations

Verify recovery successful:

System operational?

Users can access and work normally?

Performance acceptable?

Rollback to normal:

Return to primary environment

Verify normal operations

Document results:

Recovery successful?

Actual RTO vs target?

Issues encountered and resolutions

Method 5: Full Disaster Recovery Exercise (Most Comprehensive)

What it is:- Comprehensive test of entire DR capability
- Simulate complete disaster (all systems down, building unavailable)
- Execute full recovery: Restore systems, relocate staff, resume operations
- Most realistic and stressful test

Advantages:- Comprehensive validation
- Tests coordination and communication
- Identifies integration issues between procedures
- Proves organization can actually recover
- Builds confidence

Disadvantages:- Very disruptive and expensive
- Requires significant planning and coordination
- Risk of impacting production
- Stress on team

Frequency:Every 2-3 years (annual tabletop + periodic backup tests supplement)

How to conduct:

Plan extensively (months in advance):

Define scope (all systems or subset?)

Select date (weekend to minimize disruption)

Prepare test environment

Schedule all participants

Arrange alternate site if testing that

Budget for costs

Execute test:

Simulate disaster (announce scenario)

Teams execute procedures

Recover systems to test environment

Relocate staff to alternate location (if testing)

Resume business operations

Time all activities

Verify success:

Systems recovered within RTO?

Data loss within RPO?

Business functions operational?

Communication effective?

Comprehensive debrief:

What worked well?

What didn't work?

What was harder than expected?

What took longer than expected?

Team feedback

Detailed report:

Test results

RTO/RPO actuals vs targets

Issues and root causes

Recommendations

Action plan for improvements

Follow-up:

Update BRRP based on findings

Implement improvements

Retest failed components

Budget for costs

Execute test:

Time all activities

Verify success:

Communication effective?

Comprehensive debrief:

Team feedback

Detailed report:

Action plan for improvements

Follow-up:

This is most valuable test but also most resource-intensive. Worth doing periodically.

### Step 6.3: Document Test Results

Test report template:

BC/DR TEST REPORT

Test Date: [Date]
Test Type: [Tabletop / Backup Restoration / WFH / Functional / Full DR]
Scenario: [Description]
Participants: [Names and roles]

────────────────────────────────────────────────────────────────
OBJECTIVES

Goals for this test:
1. [Objective 1: e.g., "Validate order system recovery procedure"]
2. [Objective 2: e.g., "Verify RTO of 4 hours achievable"]
3. [Objective 3: e.g., "Test team coordination and communication"]

────────────────────────────────────────────────────────────────
SUMMARY

Overall assessment: [SUCCESSFUL / SUCCESSFUL WITH ISSUES / UNSUCCESSFUL]

Key findings:
- [Finding 1]
- [Finding 2]
- [Finding 3]

────────────────────────────────────────────────────────────────
DETAILED RESULTS

[For each objective, describe what happened]

Objective 1: [Objective name]
Result: [MET / PARTIALLY MET / NOT MET]
Details: [What happened, what worked, what didn't]

Timeline:
- [Time]: [Event/action]
- [Time]: [Event/action]

RTO/RPO (if applicable):
- Target RTO: [X hours]
- Actual recovery time: [X hours]
- Assessment: [Met target / Exceeded target / Did not meet target]

────────────────────────────────────────────────────────────────
ISSUES IDENTIFIED

Issue 1: [Description]
- Severity: [HIGH / MEDIUM / LOW]
- Impact: [What could go wrong in real disaster]
- Root cause: [Why this issue occurred]
- Recommendation: [How to fix]
- Owner: [Who will fix]
- Due date: [When]

Issue 2: [Description]
[Same structure]

────────────────────────────────────────────────────────────────
STRENGTHS / WHAT WORKED WELL

1. [Strength 1]
2. [Strength 2]
3. [Strength 3]

────────────────────────────────────────────────────────────────
ACTION ITEMS

1. [Action 1] - Owner: [Name] - Due: [Date] - Status: [Open/Complete]
2. [Action 2] - Owner: [Name] - Due: [Date] - Status: [Open/Complete]

────────────────────────────────────────────────────────────────
NEXT STEPS

- Implement action items by [date]
- Update BRRP procedures based on findings
- Retest [specific items] in [timeframe]
- Next scheduled test: [Date and type]

────────────────────────────────────────────────────────────────
COMPLIANCE

This test satisfies:
☐ SOC 2 annual BC/DR testing requirement
☐ HIPAA contingency plan testing requirement
☐ ISO 27001 business continuity testing requirement
☐ Internal policy requirement

Evidence retained: Test plan, test report, attendance, documentation

Test documentation required for compliance:- Test plan (what you'll test)
- Test report (what happened)
- Issues identified and remediation
- Sign-off by management

Retain for: 3+ years (audit evidence)

### Step 6.4: Follow-Up and Continuous Improvement

After every test:

Fix issues immediately:

Critical issues (test failures): Fix before next production day

High issues: Fix within 30 days

Medium/low issues: Fix within quarter

Update BRRP:

Revise procedures based on findings

Update contact information if outdated

Clarify unclear steps

Add missing steps

Retest if major issues:

If test largely failed, retest after fixes implemented

Confirm remediation effective

Track improvements over time:

Compare test results year-over-year

RTO improving or getting worse?

Fewer issues identified over time? (Good! Program maturing)

Communicate results:

Brief management on test results

Share lessons learned with team

Celebrate successes

Medium/low issues: Fix within quarter

Update BRRP:

Add missing steps

Retest if major issues:

Confirm remediation effective

Track improvements over time:

Fewer issues identified over time? (Good! Program maturing)

Communicate results:

Building a testing culture:

Testing isn't punishment, it's practice

Everyone makes mistakes in tests - that's the point (find problems when stakes are low)

Frame positively: "Great test! We found 5 issues we can fix before a real disaster"

Make testing routine, not scary

Your BC/DR program is only as good as your last test.

## Appendices

### Appendix A: Implementation Timeline

Sample 6-Month Implementation Timeline:

| Month | Weeks | Activities |
| --- | --- | --- |
| Month 1 | Weeks 1-4 | - Secure executive sponsorship- Conduct Business Impact Analysis (BIA)- Identify critical functions and RTO/RPO |
| Month 2 | Weeks 5-8 | - Conduct risk assessment- Develop continuity strategies- Begin documenting DR procedures |
| Month 3 | Weeks 9-12 | - Complete DR procedures- Document BC procedures- Create communication templates |
| Month 4 | Weeks 13-16 | - Finalize BRRP document- Management review and approval- Staff training and awareness |
| Month 5 | Weeks 17-20 | - First tabletop exercise- Backup restoration test- Refine procedures based on testing |
| Month 6 | Weeks 21-24 | - Final procedures updates- Distribute BRRP to team- Schedule ongoing testing program- Program officially launched |

Accelerated 3-Month Timeline (SMB):

| Month | Activities |
| --- | --- |
| Month 1 | BIA (1 week) + Risk Assessment (1 week) + Strategy Development (2 weeks) |
| Month 2 | Document Procedures (3 weeks) + Communication Planning (1 week) |
| Month 3 | Testing (2 weeks) + Finalization (2 weeks) |

### Appendix B: Budget Worksheet

Sample BC/DR Budget (SMB):

| Item | Purpose | Annual Cost |
| --- | --- | --- |
| Cloud backup service | Daily backups, offsite storage | $1,200 |
| Backup internet (cellular) | ISP redundancy | $600 |
| Executive suite (standby) | Pre-arrangement for alternate site | $500 |
| Testing costs | Time and potential downtime | $2,000 |
| Training | Staff training and exercises | $1,000 |
| Documentation and tools | Templates, software | $500 |
| Total Annual |  | $5,800 |

Sample BC/DR Budget (Enterprise):

| Item | Purpose | Annual Cost |
| --- | --- | --- |
| Enterprise backup solution | Backup software, storage, management | $50,000 |
| Cloud DR services | Alternate infrastructure, failover | $75,000 |
| Redundant systems | High availability infrastructure | $100,000 |
| Alternate site (warm site) | Pre-contracted recovery facility | $30,000 |
| Testing program | Regular exercises, consulting | $25,000 |
| BC software | BC planning and management tools | $10,000 |
| Training and awareness | All-staff training, specialized training | $15,000 |
| Staff time | BC Manager role (FTE or partial) | $80,000 |
| Total Annual |  | $385,000 |

Note: Significant first-year costs for implementation and setup; ongoing costs lower

### Appendix C: Tool Recommendations

Backup and DR Tools:-Backup:Veeam, Commvault, Rubrik, Acronis, Backblaze, Carbonite
-Cloud DR:AWS Elastic Disaster Recovery, Azure Site Recovery, VMware Cloud DR
-DR-as-a-Service:Sungard, Zerto, IBM Resiliency Services

BC Planning and Management:-Planning tools:Fusion Risk Management, Castellan, Everbridge, Preparis
-Communication:Everbridge, AlertMedia, OnSolve
-Documentation:Microsoft 365, Google Workspace, Confluence
-Training and testing:Castellan, Fusion, or custom exercises

Monitoring and Alerting:-System monitoring:Datadog, New Relic, Nagios, Zabbix
-Uptime monitoring:Pingdom, UptimeRobot, StatusCake

Collaboration and Communication:-Video conferencing:Zoom, Microsoft Teams, Google Meet
-Chat:Slack, Microsoft Teams
-Project management:Asana, Monday.com, Jira

Congratulations! You now have a roadmap to build a comprehensive BC/DR program.

Remember:- Start with BIA (know what's critical)
- Test regularly (untested plans fail)
- Update continuously (business changes)
- Communicate clearly (keep everyone informed)
- Practice makes perfect (the more you test, the better you'll be)

Good luck with your BC/DR implementation!