## Lists (hidden)
Cybersecurity and Information Security | 5 - Very High | 5 - Catastrophic | Effective | Mitigate | Critical | Active | Not Started | Preventive Control | L: 1, I: 1 = Score 1
Operational and Technology | 4 - High | 4 - Major | Partially Effective | Accept | High | Monitoring | In Progress | Detective Control | L: 1, I: 2 = Score 2
Compliance and Regulatory | 3 - Medium | 3 - Moderate | Ineffective | Transfer | Medium | Mitigated | Blocked | Corrective Control | L: 1, I: 3 = Score 3
Third-Party and Vendor | 2 - Low | 2 - Minor | None | Avoid | Low | Accepted | Complete | Risk Transfer | L: 1, I: 4 = Score 4
Business Continuity and Disaster Recovery | 1 - Very Low | 1 - Negligible |  |  |  | Closed | Cancelled | Process Improvement | L: 1, I: 5 = Score 5
Human Capital and Insider | [7 empty] | Technical Implementation | L: 2, I: 1 = Score 2
Financial and Fraud | [7 empty] | Training/Awareness | L: 2, I: 2 = Score 4
Reputational and Brand | [7 empty] | Policy Update | L: 2, I: 3 = Score 6
Strategic and Market | [7 empty] | Other | L: 2, I: 4 = Score 8
Physical and Environmental | [8 empty] | L: 2, I: 5 = Score 10
L: 3, I: 1 = Score 3
L: 3, I: 2 = Score 6
L: 3, I: 3 = Score 9
L: 3, I: 4 = Score 12
L: 3, I: 5 = Score 15
L: 4, I: 1 = Score 4
L: 4, I: 2 = Score 8
L: 4, I: 3 = Score 12
L: 4, I: 4 = Score 16
L: 4, I: 5 = Score 20
L: 5, I: 1 = Score 5
L: 5, I: 2 = Score 10
L: 5, I: 3 = Score 15
L: 5, I: 4 = Score 20
L: 5, I: 5 = Score 25

## Risk_Scenarios
Risk ID | Risk Category | Risk Name | Risk Description | Threat Source | Vulnerabilities | Likelihood (Inherent) | Impact (Inherent) | Inherent Risk Score | Inherent Risk Rating | Existing Controls | Control Effectiveness | Likelihood (Residual) | Impact (Residual) | Residual Risk Score | Residual Risk Rating | Risk Response Strategy | Risk Owner | Additional Mitigation Needed | Target Residual Risk | Mitigation Priority | Risk Indicators (KRIs) | Last Review Date | Next Review Date | Status | Notes
RISK-001 | Cybersecurity and Information Security | Ransomware Attack on Production Database | Ransomware malware deployed via phishing email or vulnerability exploit encrypts production database servers, making customer data and core application unavailable. Attackers demand payment for decryption keys. | External threat actors (cybercriminal groups), potentially insider enabling access | Unpatched server vulnerabilities; limited email filtering; insufficient endpoint protection; single factor authentication for some admin accounts; limited network segmentation; inadequate backup validation | 4 - High | 5 - Catastrophic | 20 | Critical | Email filtering and anti-phishing tools; Endpoint detection and response (EDR) on workstations; Regular vulnerability scanning; Daily backups with 30-day retention; Incident response plan; Security awareness training (quarterly); Network firewall and IDS | Partially Effective | 3 - Medium | 4 - Major | 12 | Medium | Mitigate | Michael Rodriguez (CISO) | Implement mandatory MFA for all admin accounts; Deploy EDR on all servers; Implement network segmentation isolating critical databases; Conduct tabletop exercise for ransomware response; Implement offline/immutable backups; Enhance email security with sandboxing; Accelerate patching cycle to <7 days | L: 2, I: 3 = Score 6 | High | Failed login attempts; Phishing email click rate; Patching compliance %; EDR alert volume; Backup success rate; Mean time to patch | 2025-01-15 | 2025-04-15 | Active | Similar ransomware attacks affected 3 competitors in past 12 months. Board is monitoring progress quarterly. Cyber insurance renewed with $5M coverage.

## Mitigation_Actions
Action ID | Related Risk ID | Risk Name | Mitigation Action | Action Type | Owner | Priority | Target Completion Date | Status | % Complete | Actual Completion Date | Cost/Budget | Expected Risk Reduction | Effectiveness Validation | Notes

## Risk_Heat_Map
Inherent Risk Heat Map (Likelihood vs Impact)
| Impact → | 1 | 2 | 3 | 4 | 5
5
4
3
2
1
Tip: Paste Risk IDs into the grid based on Likelihood (rows) and Impact (columns).
Residual Risk Heat Map (Likelihood vs Impact)
| Impact → | 1 | 2 | 3 | 4 | 5
5
4
3
2
1
Tip: Paste Risk IDs into the grid based on Likelihood (rows) and Impact (columns).
Target Risk Heat Map (Likelihood vs Impact)
| Impact → | 1 | 2 | 3 | 4 | 5
5
4
3
2
1
Tip: Paste Risk IDs into the grid based on Likelihood (rows) and Impact (columns).

## Risk_Categories_Summary
Risk Category | # of Risks | # Critical/High Risks | Avg Inherent Risk Score | Avg Residual Risk Score | Risk Reduction | % Risk Reduction | # Risks Needing Mitigation | Top 3 Risks
Cybersecurity and Information Security | [7 empty] | Use filter or pivot to list top risks
Operational and Technology | [7 empty] | Use filter or pivot to list top risks
Compliance and Regulatory | [7 empty] | Use filter or pivot to list top risks
Third-Party and Vendor | [7 empty] | Use filter or pivot to list top risks
Business Continuity and Disaster Recovery | [7 empty] | Use filter or pivot to list top risks
Human Capital and Insider | [7 empty] | Use filter or pivot to list top risks
Financial and Fraud | [7 empty] | Use filter or pivot to list top risks
Reputational and Brand | [7 empty] | Use filter or pivot to list top risks
Strategic and Market | [7 empty] | Use filter or pivot to list top risks
Physical and Environmental | [7 empty] | Use filter or pivot to list top risks

## Executive_Dashboard
Executive Risk Dashboard
Metric | Value | Severity | Count | Category | Count | Metric | Score
Total Risks Identified |  | Critical |  | Cybersecurity and Information Security |  | Avg Inherent
Critical Risks (20-25) |  | High |  | Operational and Technology |  | Avg Residual
High Risks (15-19) |  | Medium |  | Compliance and Regulatory
Medium Risks (10-14) |  | Low |  | Third-Party and Vendor
Low Risks (1-9) |  |  |  | Business Continuity and Disaster Recovery
Total Mitigation Actions |  |  |  | Human Capital and Insider
Actions Complete |  |  |  | Financial and Fraud
Actions In Progress |  |  |  | Reputational and Brand
Actions Not Started |  |  |  | Strategic and Market
Actions Overdue |  |  |  | Physical and Environmental
% Mitigation Complete
Avg Inherent Risk Score
Avg Residual Risk Score
Avg Risk Reduction
Risks Reviewed This Quarter
Risks Overdue for Review

## Risk_Assessment_History
Risk ID | Assessment Date | Assessment Period | Likelihood (Residual) | Impact (Residual) | Residual Risk Score | Risk Rating | Changes Since Last Assessment | Assessor

## Risk_Scenario_Templates
Risk ID | Risk Category | Risk Name | Risk Description | Threat Source | Vulnerabilities | Likelihood (Inherent) | Impact (Inherent) | Inherent Risk Score | Inherent Risk Rating | Existing Controls | Control Effectiveness | Likelihood (Residual) | Impact (Residual) | Residual Risk Score | Residual Risk Rating | Risk Response Strategy | Risk Owner | Additional Mitigation Needed | Target Residual Risk | Mitigation Priority | Risk Indicators (KRIs) | Last Review Date | Next Review Date | Status | Notes
TEMP-001 | Cybersecurity and Information Security | Ransomware attack encrypting critical systems | [21 empty] | Monitoring
TEMP-002 | Cybersecurity and Information Security | Phishing attack compromising employee credentials | [21 empty] | Monitoring
TEMP-003 | Business Continuity and Disaster Recovery | Cloud provider outage causing service disruption | [21 empty] | Monitoring
TEMP-004 | Third-Party and Vendor | Critical vendor data breach affecting our data | [21 empty] | Monitoring
TEMP-005 | Human Capital and Insider | Insider threat exfiltrating sensitive data | [21 empty] | Monitoring
TEMP-006 | Operational and Technology | Failed system migration causing extended outage | [21 empty] | Monitoring
TEMP-007 | Compliance and Regulatory | GDPR non-compliance resulting in regulatory fines | [21 empty] | Monitoring
TEMP-008 | Human Capital and Insider | Key personnel departure taking critical knowledge | [21 empty] | Monitoring
TEMP-009 | Physical and Environmental | Natural disaster destroying primary data center | [21 empty] | Monitoring
TEMP-010 | Cybersecurity and Information Security | DDoS attack making services unavailable | [21 empty] | Monitoring
TEMP-011 | Cybersecurity and Information Security | Privilege escalation via misconfigured IAM | [21 empty] | Monitoring
TEMP-012 | Cybersecurity and Information Security | Compromised API keys used for data extraction | [21 empty] | Monitoring
TEMP-013 | Financial and Fraud | Financial fraud through invoice spoofing | [21 empty] | Monitoring
TEMP-014 | Reputational and Brand | Public relations crisis due to social media incident | [21 empty] | Monitoring
TEMP-015 | Strategic and Market | Loss of major customer due to SLA breaches | [21 empty] | Monitoring
TEMP-016 | Third-Party and Vendor | Third-party SaaS outage impacting operations | [21 empty] | Monitoring
TEMP-017 | Operational and Technology | Endpoint malware outbreak due to USB devices | [21 empty] | Monitoring
TEMP-018 | Business Continuity and Disaster Recovery | Data loss from failed backup restoration | [21 empty] | Monitoring
TEMP-019 | Physical and Environmental | Physical break-in compromising servers | [21 empty] | Monitoring
TEMP-020 | Compliance and Regulatory | Compliance lapse in SOC 2 controls | [21 empty] | Monitoring
TEMP-021 | Operational and Technology | Misconfiguration exposes database to internet | [21 empty] | Monitoring
TEMP-022 | Operational and Technology | Supply chain attack via compromised dependency | [21 empty] | Monitoring
TEMP-023 | Compliance and Regulatory | Legal action due to privacy incident | [21 empty] | Monitoring
TEMP-024 | Cybersecurity and Information Security | Unauthorized access due to weak MFA coverage | [21 empty] | Monitoring
TEMP-025 | Operational and Technology | Change failure causing production rollback | [21 empty] | Monitoring